## AWPB 2018-19
FISCAL YEAR | COMPONENT | OUTPUT/SUBCOMPONENT | OUTPUT CODE | ACTIVITY | ACTIVITY CODE | SUBACTIVITY | INDICATOR | UNIT | PHYSICAL TARGET | PROPOSED BUDGET (AWPB) | FUND SOURCE | FUNDING CATEGORY | TIME FRAME | AGENCY | SECTOR | PROCUREMENT PLAN | REMARKS
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 1 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 2 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | LHUENTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of farmers trained | No | 3 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 2 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.025 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 2. Upgrading of farm roads to climate resilient standards | No. of scheme | No | 1 | 1.08 | IFAD LOAN | WORKS | Q1-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 3. Capacity development of existing farmer groups, WUG and RUG | No. of Events | No | 1 | 0.054 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of events | No | 1 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of farmers trained | No | 200 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of farmers trained | No | 600 | 1.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of farmers trained | No | 200 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of farmers trained | No | 600 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of Events | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Quantity of materials supplied | Acre | 90 | 1.5 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | LHUENTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 15 | 0.225 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 4 | 0.08 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 30 | 0.45 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of Events | No | 1 | 0.195 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 5 | 0.35 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 6 | 0.156 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 2 | 0.078 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 4 | 0.104 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.26 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 7. Retraining on farm record keeping | No. of groups trained | No | 10 | 0.26 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 30 | 0.875 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | YES | Revised on 30/08/2018
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 3 | 0.048 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 15 | 0.51 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 15 | 0.153 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q3-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 4 | 0.208 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 50 | 0.15 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 60 | 2.872 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | NO | Revised on 30/08/2018
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 50 | 1.6 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q2-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | NO | Revised on 30/08/2018
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 40 | 1.09 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | YES | Revised on 30/08/2018
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 40 | 0.0109 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q3 | LHUENTSE DZONGKHAG | LIVESTOCK | NO | Revised on 30/08/2018
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 8 | 1.04 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 14 | 1.54 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | LHUENTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 1. Construction of milk collection sheds | No. of shed constructed | No | 3 | 0.51 | IFAD LOAN | WORKS | Q2-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 3. Construction of milk collection centers with chilling facilities | No. of shed constructed | No | 1 | 1.5 | IFAD LOAN | WORKS | Q2-Q4 | LHUENTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 1 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 3 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | MONGAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of Events | No | 3 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 2 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.025 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 2. Water Users Associations (O&M) | No. of groups upgraded | No | 1 | 0.028 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 5. Renovation of irrigation infrastructure | No. of scheme | No | 1 | 5 | IFAD LOAN | WORKS | Q1-Q4 | MONGAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of Events | No | 1 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of farmers trained | No | 200 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of farmers trained | No | 9 | 1.63 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of farmers trained | No | 30 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of farmers trained | No | 15 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of farmers trained | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | MONGAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | MONGAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Area covered | Acre | 50 | 1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | MONGAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 15 | 0.225 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 7 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 100 | 1.5 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q3 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of groups trained | No | 3 | 0.585 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 6 | 0.338 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 11 | 0.286 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 6 | 0.234 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 11 | 0.286 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 6 | 0.312 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 20 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 5 | 0.08 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 10 | 1.3 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 10 | 0.39 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 8 | 0.416 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 215 | 0.645 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 40 | 1.8 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 40 | 0.99 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 1.26 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 0.126 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q2 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 6 | 0.78 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of farmers trained | No | 30 | 3.03 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1 | MONGAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 3. Construction of milk collection centers with chilling facilities | No. of MCC constructed | No | 1 | 1.5 | IFAD LOAN | WORKS | Q3-Q4 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 6. Milk analyzer | No. of equipments supplied | No | 2 | 0.106 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | MONGAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 4 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 34 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of farmers trained | No | 12 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 1 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.025 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 2. Upgrading of farm roads to climate resilient standards | No. of scheme | No | 1 | 1.083 | IFAD LOAN | WORKS | Q1 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 3. Capacity development of existing farmer groups, WUG and RUG | No. of groups trained | No | 1 | 0.054 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of Events | No | 8 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of farmers trained | No | 200 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of farmers trained | No | 600 | 1.3 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of farmers trained | No | 200 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of farmers trained | No | 600 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of farmers trained | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Area covered | Acre | 50 | 1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | PEMAGATSHEL DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 10 | 0.15 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 10 | 0.2 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 40 | 0.6 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of groups trained | No | 2 | 0.39 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 3 | 0.195 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 4 | 0.156 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.13 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 7. Retraining on farm record keeping | No. of groups trained | No | 12 | 0.312 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 50 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 6 | 0.096 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 5 | 0.65 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 5 | 0.195 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 5 | 0.26 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 100 | 0.3 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 20 | 0.9 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 20 | 0.495 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 30 | 0.84 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 30 | 0.084 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 5 | 0.65 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups upgraded | No | 2 | 0.2 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 1. Construction of milk collection sheds | No. of shed constructed | No | 3 | 0.585 | IFAD LOAN | WORKS | Q2-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 3. Construction of milk collection centers with chilling facilities | No. of MCC constructed | No | 1 | 1.5 | IFAD LOAN | WORKS | Q2-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 7. Milk processing unit | No. of MPU established | No | 1 | 2.34 | IFAD LOAN | WORKS | Q2-Q4 | PEMAGATSHEL DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 1 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | No. of Events | No | 2 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of farmers trained | No | 3 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 2 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.025 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 2. Water Users Associations (O&M) | No. of groups trained | No | 1 | 0.028 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 5. Renovation of irrigation infrastructure | No. of scheme | No | 1 | 4 | IFAD LOAN | WORKS | Q2-Q4 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of Events | No | 1 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of groups trained | No | 4 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of groups trained | No | 5 | 1.458 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of groups trained | No | 3 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of groups trained | No | 3 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of farmers trained | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Area covered | Acre | 50 | 1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 10 | 0.15 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 10 | 0.2 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 4. Bee Keeping | No.of HH | No | 30 | 0.45 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q2 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 50 | 0.75 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of groups trained | No | 1 | 0.195 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 2 | 0.13 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 9 | 0.234 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 5 | 0.195 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.26 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 7. Retraining on farm record keeping | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 20 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 6 | 0.096 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 13 | 1.69 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 13 | 0.507 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 5 | 0.26 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 500 | 0.5 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 30 | 1.35 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 30 | 0.743 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q3-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 1.26 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 0.126 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 150 | 0.7 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 5 | 0.505 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 1. Construction of milk collection sheds | No. of shed constructed | No | 10 | 1.7 | IFAD LOAN | WORKS | Q1-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 3. Construction of milk collection centers with chilling facilities | No. of MCC constructed | No | 2 | 2 | IFAD LOAN | WORKS | Q2-Q4 | SAMDRUP JONGKHAR DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 1 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 3 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | TRASHIGANG DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of farmers trained | No | 4 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 1 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.029 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 2. Water Users Associations (O&M) | No. of groups trained | No | 1 | 0.028 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 5. Renovation of irrigation infrastructure | No. of scheme | No | 2 | 5 | IFAD LOAN | WORKS | Q3 | TRASHIGANG DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of groups upgraded | No | 6 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of farmers trained | No | 200 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of farmers trained | No | 600 | 1.3 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of farmers trained | No | 200 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of farmers trained | No | 600 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of farmers trained | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | TRASHIGANG DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Area covered | Acre | 90 | 1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | TRASHIGANG DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 10 | 0.15 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 5 | 0.1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 100 | 1.5 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of groups trained | No | 2 | 0.39 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 5 | 0.325 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 10 | 0.26 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 8 | 0.312 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 10 | 0.312 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.13 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 7. Retraining on farm record keeping | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 20 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 5 | 0.08 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 10 | 1.3 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 10 | 0.39 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 8 | 0.416 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 200 | 0.6 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 30 | 1.35 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 30 | 0.743 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 1.26 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 45 | 0.126 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 8 | 1.04 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHIGANG DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 1 | 0.101 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHIGANG DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 1. Upgrading of existing farmer groups | No. of groups upgraded | No | 1 | 0.043 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 1 | 0.216 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 5. Up-scaling of Lead Farmer Training Model | No. of farmers trained | No | 3 | 0.182 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 6. Farmer field festivals | No. of Events | No | 2 | 0.147 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 1 | 0.025 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 2. Upgrading of farm roads to climate resilient standards | No. of scheme | No | 1 | 1.083 | IFAD LOAN | WORKS | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 3. Capacity development of existing farmer groups, WUG and RUG | No. of Events | No | 3 | 0.054 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 1. Awareness & Mobilization | No. of farmers trained | No | 50 | 0.203 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 2. Training on vegetable production techniques | No. of farmers trained | No | 200 | 0.563 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 3. Retraining on vegetable production techniques | No. of farmers trained | No | 600 | 0.813 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 4. Training on post-harvest management | No. of farmers trained | No | 200 | 0.558 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 5. Retraining on post-harvest management | No. of farmers trained | No | 600 | 0.704 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.B. Capacity Development of Vegetable Production Groups | ACTIVITY1.2.B | 6. Exchange visits for farmers | No. of farmers trained | No | 12 | 0.18 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 1. Provision of stress tolorent vegetable seeds | Qunatity of seeds supplied | Acre | 4 | 0.27 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 2. Water efficient irrigation | Area covered | Acre | 90 | 1.5 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 4. Poultry for farm resilience and diversification | Unit of native poultry farm established | No | 10 | 0.15 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 5. Piggery for farm resilience and diversification | unit of native piggery established | No | 2 | 0.04 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of equipments supplied | No | 10 | 0.15 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q2-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 1. Awareness & Mobilization | No. of groups trained | No | 4 | 0.78 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 2. Training on livestock husbandry | No. of groups trained | No | 5 | 0.325 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 3. Retraining on livestock husbandry | No. of groups trained | No | 3 | 0.078 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 4. Training on clean milk production | No. of groups trained | No | 3 | 0.117 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 5. Retraining on clean milk production | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 6. Training on farm record keeping | No. of groups trained | No | 5 | 0.13 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.B. Capacity Development of Dairy Production Groups | ACTIVITY1.3.B | 7. Retraining on farm record keeping | No. of groups trained | No | 5 | 0.13 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 1. Perenial fodder in fallow and marginal land | Area covered | Acre | 20 | 0.14 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 2. Winter fodder crop demonstration and seed supply | Area covered | Acre | 3 | 0.048 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 4 | 0.132 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 4. Chopping machine (for dairy groups) | No. of equipments supplied | No | 4 | 0.04 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 5. Training on use of crop residues and feed/fodder | No. of Events | No | 4 | 0.2 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 1. Milk cans | No. of equipments supplied | No | 40 | 0.12 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 20 | 0.9 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 2. Cross-breed cattle | No. of cows supplied | No | 20 | 0.495 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 20 | 0.56 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
| COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 3. Shed construction | No. of shed constructed | No | 20 | 0.056 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q3 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 30 | 0.13 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 10 | 1 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 1. Construction of milk collection sheds | No. of shed constructed | No | 1 | 0.3 | IFAD LOAN | WORKS | Q3-Q4 | TRASHI YANGTSE DZONGKHAG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 2. Training of extension agents | No. of Extension trained | No | 30 | 0.69 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 3. Agricultural inputs for farm resilience and diversification | Area covered | Acre | 10 | 3.75 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 9. Crop diversification(Cereals, oil seeds, pulses& fruits) | Area covered | Acre | 12 | 0.9 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q2 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 1. Farm level rainwater harvesting infrastucture | No. of Infrastructure established | No | 2 | 0.8 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q4 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 2. Seed and seedlings | Area covered | Acre | 50 | 0.75 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 3. Tools for permaculture | Set of tools supplied | Set | 7 | 1.75 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q2-Q4 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 6. Training course on permaculture | No. of Events | No | 1 | 0.6 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 2. Training of lead farmers | No. of farmers trained | No | 40 | 1.6 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 7. Workshops (planning, review, evaluation) | No. of Events | No | 3 | 0.45 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 8. Documentation and systematization | Documents produced | No | 1 | 0.25 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 9. Demonstration inputs for lead farmer | Area covered | Acre | 40 | 1.4 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 10. Poly-tunnels for lead farmers | No. of equipments supplied | No | 40 | 0.8 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 6. Pilot irrigation schemes | No. of pilot schemes developed | No | 4 | 21.2 | IFAD LOAN | WORKS | Q2 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 7. Quality control and supervision | No. of quality control & supervision conducted | No | 4 | 0.5 | IFAD LOAN | WORKS | Q2-Q3 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.C. Vegetable Seed Research & Production | ACTIVITY1.2.C | 1. Developing packages of practice (extension material) | No. of Extension materials produced | No | 2 | 0.52 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.C. Vegetable Seed Research & Production | ACTIVITY1.2.C | 2. Training and certification of vegetable seed growers | No. of seed growers | No | 20 | 0.28 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.C. Vegetable Seed Research & Production | ACTIVITY1.2.C | 3. Equipment and input support vegetable seed growers | No. of equipments supplied | No | 7 | 2.1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 3. Small post-harvest equipments | No. of equipments supplied | No | 20 | 1.8 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 3. Small post-harvest equipments | No. of equipments supplied | No | 20 | 0.36 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q3 | ARDC WENGKHAR | AGRICULTURE | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.A. Climate Smart Agriculture Production and Management | ACTIVITY1.1.A | 2. Training of extension agents | No. of Extension trained | No | 42 | 1.2 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 4. Bee Keeping | No. HH supported | No | 6 | 0.3 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.D. Increase Outreach of Extension Services through Lead Farmer Model | ACTIVITY1.1.D | 3. Development of training material and field manuals | Documents produced | No | 2 | 0.245 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.A. Development of training materials | ACTIVITY1.3.A | 1. Development of training materials | Documents produced | No | 3 | 1.3 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q2-Q3 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 1. CAHW model development and packaging | No. of model developed | No | 1 | 0.975 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q2 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 2. Training of trainers (ToT) | No. of TOT conducted | No | 1 | 0.65 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 3. Training of CAHWs | No. of farmers trained | No | 20 | 0.54 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 4. Retraining of CAHWs | No. of farmers trained | No | 26 | 0.54 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 6. Transport facilities for CAHWs | No. of Bikes | No | 15 | 1.95 | IFAD GRANT | GOODS, SERVICES & INPUTS | Q1 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.C. Improved Services Outreach through CAHWs & Lead Farmers | ACTIVITY1.3.C | 7. Stipend for CAHWs | Amount disbursed | Nu | 45 | 1.463 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.D. Support to Fodder & Feed Production | ACTIVITY1.3.D | 3. Training of feed producers | No. of farmers trained | No | 10 | 0.16 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT1 | 1.3. Intensification & Expansion of Dairy Production | OUTPUT1.3 | 1.3.E. Provision of Dairy Production Inputs | ACTIVITY1.3.E | 4. Equipment dairy production groups | No. of equipments supplied | No | 60 | 3.3 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 10 | 1.075 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q2 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.C. Support to Entrepreneurs | ACTIVITY2.2.C | 1. Development of training packages for agriculture entrepreneurs | No. of Events | No | 1 | 0.65 | IFAD GRANT | GOODS, SERVICES & INPUTS | Q2-Q4 | RLDC KANGLUNG | LIVESTOCK | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 2. Equipments for milk collection shed | No. of equipments supplied | Lumpsum | Lumpsum | 0.13 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 3. Construction of milk collection centers with chilling facilities | No. of MCC constructed | No | 8 | 6.24 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | RLDC KANGLUNG | LIVESTOCK | YES | Revised on 30/08/2018 (From 2017-18 AWPB)
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 4. Milk chillers | No. of equipments supplied | No | 2 | 0.9 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 5. Milk quality test equipment | No. of equipments supplied | No | 8 | 0.078 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 6. Milk analyzer | No. of equipments supplied | No | 8 | 0.429 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 7. Milk processing unit | No. of MPU established | No | 1 | 4.68 | IFAD LOAN | WORKS | Q2 | RLDC KANGLUNG | LIVESTOCK | YES | Revised on 30/08/2018 (From 2017-18 AWPB)
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 8. Milk processing equipment | No. of equipments supplied | No |  | 4.4 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q2 | RLDC KANGLUNG | LIVESTOCK | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.C. Dairy Value-chain Post-harvest & Market Infratsructure & Equipment | ACTIVITY2.3.C | 9. Milk chilling tanker | No. of equipments supplied | No | 2 | 4.817 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2-Q4 | RLDC KANGLUNG | LIVESTOCK | YES | Revised on 30/08/2018
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.A. Support to Marketing Groups | ACTIVITY2.2.A | 3. Improve existing marketing and market channel in capacity development packages | No. of market channel strengthened | No | 6 | 4 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 1. Formation of vegetable marketing groups | No. of groups formed | No | 25 | 1.625 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 2. Formation of dairy marketing groups | No. of groups formed | No | 15 | 1.3 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.C. Support to Entrepreneurs | ACTIVITY2.2.C | 1. Development of training packages for agriculture entrepreneurs | No. of packages developed | No | 2 | 0.65 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q4 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.D. Other Trainings to Groups, Cooperatives & Entrepreneurs | ACTIVITY2.2.D | 1. Other Trainings to Groups, Cooperatives & Entrepreneurs | No. of farmers trained | No | 60 | 3.7 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.E. Multi-stakeholder Platforms & Network development | ACTIVITY2.2.E | 1. Multi-stakeholder platforms and network development | No. of Events | No | 3 | 1 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.A. Planning & Design | ACTIVITY2.3.A | 1. Business plan-based planning of market infrastructure | No. of plan developed | No | 1 | 1 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q2 | RAMCO | MARKETING | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.B. Vegetable Value-chain, Post-harvest & Market Infrastructure & Equipment | ACTIVITY2.3.B | 1. Value-chain equipment | No. of equipments supplied | No | 1 | 1.5 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | RAMCO | MARKETING | YES
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.B. Vegetable Value-chain, Post-harvest & Market Infrastructure & Equipment | ACTIVITY2.3.B | 2. Value-chain infrastructure | No. of Infrastructure established | No | 5 | 7 | IFAD LOAN | WORKS | Q2-Q3 | RAMCO | MARKETING | YES
2018-19 | COMPONENT3 | 3.1. Strengthened Value-Chain & Marketing Knowledge and Communication | OUTPUT3.1 | 3.1.A. Strengthening of the DAMC Market Information System | ACTIVITY3.1.A | 1. Strengthening of the DAMC market information system | No. of Infrastructure established | No | 1 | 1.508 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | RAMCO | MARKETING | NO
2018-19 | COMPONENT3 | 3.1. Strengthened Value-Chain & Marketing Knowledge and Communication | OUTPUT3.1 | 3.1.A. Strengthening of the DAMC Market Information System | ACTIVITY3.1.A | 2. Equipment related to Market Information System upgrade | No. of Infrastructure established | No | 1 | 2.119 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q3-Q4 | RAMCO | MARKETING | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.A. Support to Marketing Groups | ACTIVITY2.2.A | 2. Strengthening of existing marketing and cooperative capacity development packages | No. of group supported | No | 5 | 0.5 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY |  | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strengthened | OUTPUT2.2 | 2.2.A. Support to Marketing Groups | ACTIVITY2.2.A | 1. Awareness on marketing groups | No. of groups trained | No | 5 | 1 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | RAMCO | MARKETING | NO
2018-19 | COMPONENT2 | 2.1. Development of Resilient Vegetable & Dairy Value Chains | OUTPUT2.1 | 2.1.A. Strengthening of FCBL for Value Chain Development | ACTIVITY2.1.A | 2. Capacity development activities | No. of staff trained | No | 11 | 1.625 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1 | FCBL | MARKETING | NO
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 4. Training in packaging & handling | No. of groups trained | No | 40 | 2 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | FCBL | MARKETING | NO
2018-19 | COMPONENT2 | 2.3. Development of Community-driven Market Infrastructure | OUTPUT2.3 | 2.3.B. Vegetable Value-chain, Post-harvest & Market Infrastructure & Equipment | ACTIVITY2.3.B | 1. Value-chain equipments | No. of equipments supplied | No | 1 | 1.1 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q2 | FCBL | MARKETING | YES
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.D. Food Corporation of Bhutan | ACTIVITY4.1.D | 1. Material and equipment | Lumpsum | Lumpsum | NA | 2.745 | FCBL CONTRIBUTION | GOODS, SERVICES & INPUTS |  | FCBL | MARKETING | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.D. Food Corporation of Bhutan | ACTIVITY4.1.D | 2. Recurrent cost of FCBL (CM-VC & Farm Shop Operators) | Lumpsum | Lumpsum | NA | 29.9 | FCBL CONTRIBUTION | OPERATING COST |  | FCBL | MARKETING | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.B. Innovation through Permaculture & Biogas | ACTIVITY1.1.B | 9. Biogas digester | No. of Biogas established | No | 307 | 3.6 | ASAP GRANT | GOODS, SERVICES & INPUTS | Q1-Q4 | OPM | MANAGEMENT | YES
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.C. Innovation through ICTs | ACTIVITY1.1.C | 3. Training on report writing documentation and information sharing | No. of Events | No | 2 | 0.3 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.C. Innovation through ICTs | ACTIVITY1.1.C | 4. Information management dessimination | Documents produced | No | 1 | 0.2 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.E. Resilient & Water Use Efficient Irrigation Development | ACTIVITY1.1.E | 1. District engineers and extension agents (design and construction) | No. of Events | No | 1 | 0.767 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 1. Development of business model and sustainability plan for service and O&M | No. of model developed | No | 1 | 0.163 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.1. Increased production resilience and diversification in agriculture | OUTPUT1.1 | 1.1.F. Strengthening of Local Institutions on Smallholder's Climate Resilience | ACTIVITY1.1.F | 4. Updating of O&M models for irrigation and farm roads | Documents produced | No | 1 | 0.39 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.A. Development of training and extension material | ACTIVITY1.2.A | 1. Developemnt of extension materials | No. of Extension materials produced | No | 3 | 3.9 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 3. Small post-harvest equipments | No. of equipments supplied | No | 270 | 12.96 | IFAD LOAN | GOODS, SERVICES & INPUTS | Q1-Q4 | OPM | MANAGEMENT | YES
2018-19 | COMPONENT1 | 1.2. Intensification & Expansion of Vegetable Production | OUTPUT1.2 | 1.2.D. Provision of Vegetable Production Inputs | ACTIVITY1.2.D | 3. Small post-harvest equipments | No. of equipments supplied | No | 270 | 2.592 | BENEFICIARY | GOODS, SERVICES & INPUTS | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT2 | 2.1. Development of Resilient Vegetable & Dairy Value Chains | OUTPUT2.1 | 2.1.C. Value chain development, strengthening & expansion | ACTIVITY2.1.C | 1. Multistakeholders facilitation process | No. of Events | No | 3 | 2.515 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q1 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT2 | 2.1. Development of Resilient Vegetable & Dairy Value Chains | OUTPUT2.1 | 2.1.D. National/External TA | ACTIVITY2.1.D | 1. National/External TA | No. of Events | No | 1 | 3 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | OPM | MANAGEMENT | YES
2018-19 | COMPONENT2 | 2.2. Agricultural Commercialization & Enterprise Development strenghtened | OUTPUT2.2 | 2.2.B. Training on Marketing Groups | ACTIVITY2.2.B | 3. Training on marketing & value-chain | No. of groups trained | No | 40 | 8.075 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.A. Material & Equipment | ACTIVITY4.1.A | 4. Scanner | No. of equipments supplied | No | 2 | 0.1 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1 | OPM | MANAGEMENT | YES
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.A. Material & Equipment | ACTIVITY4.1.A | 6. Office equipment | No. of equipments supplied | No | 15 | 0.5 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q4 | OPM | MANAGEMENT | YES
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.B. Capacity Building | ACTIVITY4.1.B | 1. Training on gender | No. of staff trained | No | 8 | 0.15 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.B. Capacity Building | ACTIVITY4.1.B | 2. Training on knowledge management | No. of staff trained | No | 3 | 0.25 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.B. Capacity Building | ACTIVITY4.1.B | 3. Training on monitoring and evaluation | No. of staff trained | No | 3 | 0.75 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.B. Capacity Building | ACTIVITY4.1.B | 4. Training on financial management | No. of staff trained | No | 8 | 1.2 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q2 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.C. Coordination | ACTIVITY4.1.C | 1. Coordination meetings with dzongkhags | No. of Events | No | 2 | 0.65 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.C. Coordination | ACTIVITY4.1.C | 2. Attend annual Governing council meeting at Rome, Italy | No. of staff trained | No | 2 | 0.3 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.C. Coordination | ACTIVITY4.1.C | 3. Capacity development for CARLEP Stakeholders | No. of staff trained | No | 15 | 4 | ASAP GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.E. Monitoring & Evaluation | ACTIVITY4.1.E | 2. Programme Supervision Mission | No. of Events | No | 2 | 0.55 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.E. Monitoring & Evaluation | ACTIVITY4.1.E | 2. Programme Supervision Mission | No. of Events | No | 2 | 0.355 | RGOB CONTRIBUTION | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.E. Monitoring & Evaluation | ACTIVITY4.1.E | 3. Annual outcome surveys | No. of Events | No | 1 | 1.3 | IFAD LOAN | TRAINING-WORKSHOP/CONSULTANCY | Q2-Q3 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.E. Monitoring & Evaluation | ACTIVITY4.1.E | 4. Mid-term review | No. of Events | No | 1 | 1.95 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q3-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.F. Knowledge Management | ACTIVITY4.1.F | 1. Printing and publications | Lumpsum | Lumpsum | NA | 0.12 | IFAD GRANT | GOODS, SERVICES & INPUTS | Q2-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.1 | 4.1.F. Knowledge Management | ACTIVITY4.1.F | 4. Workshops and meetings | No. of Events | No | 4 | 2.016 | IFAD GRANT | TRAINING-WORKSHOP/CONSULTANCY | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.2. Recurrent Cost | OUTPUT4.2 | 4.2.A. OPM Mongar | ACTIVITY4.2.A | 1. Pay & allowances for OPM staff | No. of staff | No | 7 | 3.043 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.B. Liaison Office, Thimphu | ACTIVITY4.2.B | 2. Pay & allowances for 2 Liaison staff | No. of staff | No | 2 | 0.74 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.2. Recurrent Cost | OUTPUT4.2 | 4.2.A. OPM Mongar | ACTIVITY4.2.A | 2. Pay & allowance for Contract staff | No. of staff | No | 2 | 0.779 | RGOB CONTRIBUTION | OPERATING COST |  | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 1. Vehicle operation and Maintenance | No. of vehicle | No | 2 | 0.5 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 2. Maintenance of Building | Lumpsum | Lumpsum | NA | 0.5 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 3. Maintenance of Equipment | Lumpsum | Lumpsum | NA | 0.1 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 4. Utilities - telephone, internet, electricity, water, fax, sewarage, post, etc. | Lumpsum | Lumpsum | NA | 0.502 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 5. Office supplies | Lumpsum | Lumpsum | NA | 0.198 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.1. Project Management Unit | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 6. Travel | Lumpsum | Lumpsum | NA | 2.058 | RGOB CONTRIBUTION | OPERATING COST | Q1-Q4 | OPM | MANAGEMENT | NO
2018-19 | COMPONENT4 | 4.2. Recurrent Cost | OUTPUT4.2 | 4.2.C. Operating Cost, Project Management Unit | ACTIVITY4.2.C | 7. Others | Lumpsum | Lumpsum | NA | 0.437 | RGOB CONTRIBUTION | OPERATING COST |  | OPM | MANAGEMENT | NO

## FUND SOURCE
Row Labels | Sum of PROPOSED BUDGET (AWPB)
ASAP GRANT | 66.288
BENEFICIARY | 10.2219
FCBL CONTRIBUTION | 32.645
IFAD GRANT | 15.124
IFAD LOAN | 177.002
RGOB CONTRIBUTION | 25.895
Grand Total | 327.1759

## AGENCY_FUND SOURCE
Row Labels | Sum of PROPOSED BUDGET (AWPB)
ARDC WENGKHAR | 40.5
ASAP GRANT | 8.59
BENEFICIARY | 0.36
IFAD LOAN | 31.55
FCBL | 37.37
FCBL CONTRIBUTION | 32.645
IFAD LOAN | 4.725
LHUENTSE DZONGKHAG | 21.1199
ASAP GRANT | 3.158
BENEFICIARY | 1.7639
IFAD GRANT | 0.078
IFAD LOAN | 13.766
RGOB CONTRIBUTION | 2.354
MONGAR DZONGKHAG | 27.348
ASAP GRANT | 4.768
BENEFICIARY | 1.506
IFAD GRANT | 0.234
IFAD LOAN | 17.804
RGOB CONTRIBUTION | 3.036
OPM | 61.51
ASAP GRANT | 23.505
BENEFICIARY | 2.592
IFAD GRANT | 9.426
IFAD LOAN | 16.775
RGOB CONTRIBUTION | 9.212
PEMAGATSHEL DZONGKHAG | 18.156
ASAP GRANT | 3.4
BENEFICIARY | 0.774
IFAD GRANT | 0.156
IFAD LOAN | 11.25
RGOB CONTRIBUTION | 2.576
RAMCO | 26.902
ASAP GRANT | 5.325
IFAD GRANT | 1.95
IFAD LOAN | 18.127
RGOB CONTRIBUTION | 1.5
RLDC KANGLUNG | 36.022
ASAP GRANT | 5.91
IFAD GRANT | 2.6
IFAD LOAN | 27.512
SAMDRUP JONGKHAR DZONGKHAG | 23.978
ASAP GRANT | 3.686
BENEFICIARY | 1.376
IFAD GRANT | 0.223
IFAD LOAN | 16.037
RGOB CONTRIBUTION | 2.656
TRASHI YANGTSE DZONGKHAG | 12.692
ASAP GRANT | 3.41
BENEFICIARY | 0.591
IFAD GRANT | 0.117
IFAD LOAN | 6.719
RGOB CONTRIBUTION | 1.855
TRASHIGANG DZONGKHAG | 21.578
ASAP GRANT | 4.536
BENEFICIARY | 1.259
IFAD GRANT | 0.34
IFAD LOAN | 12.737
RGOB CONTRIBUTION | 2.706
Grand Total | 327.1759

## COMPONENT
Sum of PROPOSED BUDGET (AWPB)
COMPONENT | Total
COMPONENT1 | 184.4499
COMPONENT2 | 83.406
COMPONENT3 | 3.627
COMPONENT4 | 55.693
Grand Total | 327.1759

## COMPONENT_ACTIVITY
Sum of PROPOSED BUDGET (AWPB)
COMPONENT | SUBACTIVITY | Total
COMPONENT1 | 1. Awareness & Mobilization | 3.753
| 1. CAHW model development and packaging | 0.975
| 1. Developemnt of extension materials | 3.9 |  | 330
| 1. Developing packages of practice (extension material) | 0.52
| 1. Development of business model and sustainability plan for service and O&M | 0.163
| 1. Development of training materials | 1.3
| 1. District engineers and extension agents (design and construction) | 0.767
| 1. Farm level rainwater harvesting infrastucture | 0.8 | 4.95
| 1. Milk cans | 2.315
| 1. Perenial fodder in fallow and marginal land | 1.575
| 1. Provision of stress tolorent vegetable seeds | 1.62
| 1. Upgrading of existing farmer groups | 0.258
| 10. Poly-tunnels for lead farmers | 0.8
| 2. Cross-breed cattle | 14.238
| 2. Seed and seedlings | 0.75
| 2. Training and certification of vegetable seed growers | 0.28
| 2. Training of extension agents | 1.89
| 2. Training of lead farmers | 1.6
| 2. Training of trainers (ToT) | 0.65
| 2. Training on livestock husbandry | 1.663
| 2. Training on vegetable production techniques | 3.378
| 2. Upgrading of farm roads to climate resilient standards | 3.246
| 2. Water efficient irrigation | 7
| 2. Water Users Associations (O&M) | 0.084
| 2. Winter fodder crop demonstration and seed supply | 0.448
| 3. Agricultural inputs for farm resilience and diversification | 5.046
| 3. Capacity development of existing farmer groups, WUG and RUG | 0.162
| 3. Development of training material and field manuals | 0.245
| 3. Equipment and input support vegetable seed growers | 2.1
| 3. Retraining on livestock husbandry | 1.144
| 3. Retraining on vegetable production techniques | 7.631
| 3. Shed construction | 6.7989
| 3. Small post-harvest equipments | 17.712
| 3. Tools for permaculture | 1.75
| 3. Training of CAHWs | 0.54
| 3. Training of feed producers | 0.16
| 3. Training on report writing documentation and information sharing | 0.3
| 4. Bee Keeping | 0.75
| 4. Chopping machine (for dairy groups) | 7.257
| 4. Equipment dairy production groups | 7.64
| 4. Information management dessimination | 0.2
| 4. Poultry for farm resilience and diversification | 1.05
| 4. Retraining of CAHWs | 0.54
| 4. Training on clean milk production | 1.092
| 4. Training on post-harvest management | 3.348
| 4. Updating of O&M models for irrigation and farm roads | 0.39
| 5. Piggery for farm resilience and diversification | 0.76
| 5. Renovation of irrigation infrastructure | 14
| 5. Retraining on clean milk production | 1.092
| 5. Retraining on post-harvest management | 4.224
| 5. Training on use of crop residues and feed/fodder | 1.76
| 5. Up-scaling of Lead Farmer Training Model | 1.092
| 6. Exchange visits for farmers | 1.08
| 6. Farmer field festivals | 0.882
| 6. Pilot irrigation schemes | 21.2
| 6. Training course on permaculture | 0.6
| 6. Training on farm record keeping | 1.352
| 6. Transport facilities for CAHWs | 1.95
| 7. Quality control and supervision | 0.5
| 7. Retraining on farm record keeping | 0.962
| 7. Stipend for CAHWs | 1.463
| 7. Workshops (planning, review, evaluation) | 0.604
| 8. Documentation and systematization | 0.25
| 9. Biogas digester | 8.55
| 9. Crop diversification(Cereals, oil seeds, pulses& fruits) | 0.9
| 9. Demonstration inputs for lead farmer | 1.4
COMPONENT1 Total |  | 184.4499
COMPONENT2 | 1. Awareness on marketing groups | 1
| 1. Business plan-based planning of market infrastructure | 1
| 1. Construction of milk collection sheds | 3.095
| 1. Development of training packages for agriculture entrepreneurs | 1.3
| 1. Formation of vegetable marketing groups | 1.625
| 1. Multi-stakeholder platforms and network development | 1
| 1. Multistakeholders facilitation process | 2.515
| 1. National/External TA | 3
| 1. Other Trainings to Groups, Cooperatives & Entrepreneurs | 3.7
| 1. Value-chain equipments | 1.1
| 2. Capacity development activities | 1.625
| 2. Equipments for milk collection shed | 0.13
| 2. Formation of dairy marketing groups | 1.3
| 2. Strengthening of existing marketing and cooperative capacity development packages | 0.5
| 2. Value-chain infrastructure | 7
| 3. Construction of milk collection centers with chilling facilities | 12.74
| 3. Training on marketing & value-chain | 8.075
| 4. Milk chillers | 0.9
| 4. Training in packaging & handling | 9.451
| 5. Milk quality test equipment | 0.078
| 6. Milk analyzer | 0.535
| 7. Milk processing unit | 7.02
| 8. Milk processing equipment | 4.4
| 3. Improve existing marketing and market channel in capacity development packages | 4
| 1. Value-chain equipment | 1.5
| 9. Milk chilling tanker | 4.817
COMPONENT2 Total |  | 83.406
COMPONENT3 | 1. Strengthening of the DAMC market information system | 1.508
| 2. Equipment related to Market Information System upgrade | 2.119
COMPONENT3 Total |  | 3.627
COMPONENT4 | 1. Coordination meetings with dzongkhags | 0.65
| 1. Material and equipment | 2.745
| 1. Pay & allowances for OPM staff | 3.043
| 1. Printing and publications | 0.12
| 1. Training on gender | 0.15
| 1. Vehicle operation and Maintenance | 0.5
| 2. Attend annual Governing council meeting at Rome, Italy | 0.3
| 2. Maintenance of Building | 0.5
| 2. Pay & allowance for Contract staff | 0.779
| 2. Pay & allowances for 2 Liaison staff | 0.74
| 2. Programme Supervision Mission | 0.905
| 2. Recurrent cost of FCBL (CM-VC & Farm Shop Operators) | 29.9
| 2. Training on knowledge management | 0.25
| 3. Annual outcome surveys | 1.3
| 3. Capacity development for CARLEP Stakeholders | 4
| 3. Maintenance of Equipment | 0.1
| 3. Training on monitoring and evaluation | 0.75
| 4. Mid-term review | 1.95
| 4. Scanner | 0.1
| 4. Training on financial management | 1.2
| 4. Utilities - telephone, internet, electricity, water, fax, sewarage, post, etc. | 0.502
| 4. Workshops and meetings | 2.016
| 5. Office supplies | 0.198
| 6. Office equipment | 0.5
| 6. Travel | 2.058
| 7. Others | 0.437
COMPONENT4 Total |  | 55.693
Grand Total |  | 327.1759

## INVESTMENT CATEGORY
Sum of PROPOSED BUDGET (AWPB)
FUNDING CATEGORY | Total
GOODS, SERVICES & INPUTS | 121.9819
OPERATING COST | 38.757 | 4.9572
TRAINING-WORKSHOP/CONSULTANCY | 103.876
WORKS | 62.561
Grand Total | 327.1759

## AGENCY_ACTIVITY
Row Labels | Sum of PROPOSED BUDGET (AWPB)
ARDC WENGKHAR | 40.5
1. Developing packages of practice (extension material) | 0.52
1. Farm level rainwater harvesting infrastucture | 0.8
10. Poly-tunnels for lead farmers | 0.8
2. Seed and seedlings | 0.75
2. Training and certification of vegetable seed growers | 0.28
2. Training of extension agents | 0.69
2. Training of lead farmers | 1.6
3. Agricultural inputs for farm resilience and diversification | 3.75
3. Equipment and input support vegetable seed growers | 2.1
3. Small post-harvest equipments | 2.16
3. Tools for permaculture | 1.75
6. Pilot irrigation schemes | 21.2
6. Training course on permaculture | 0.6
7. Quality control and supervision | 0.5
7. Workshops (planning, review, evaluation) | 0.45
8. Documentation and systematization | 0.25
9. Crop diversification(Cereals, oil seeds, pulses& fruits) | 0.9
9. Demonstration inputs for lead farmer | 1.4
FCBL | 37.37
1. Material and equipment | 2.745
1. Value-chain equipments | 1.1
2. Capacity development activities | 1.625
2. Recurrent cost of FCBL (CM-VC & Farm Shop Operators) | 29.9
4. Training in packaging & handling | 2
LHUENTSE DZONGKHAG | 21.1199
1. Awareness & Mobilization | 0.398
1. Construction of milk collection sheds | 0.51
1. Milk cans | 0.15
1. Perenial fodder in fallow and marginal land | 0.875
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 4.472
2. Training on livestock husbandry | 0.35
2. Training on vegetable production techniques | 0.563
2. Upgrading of farm roads to climate resilient standards | 1.08
2. Water efficient irrigation | 1.5
2. Winter fodder crop demonstration and seed supply | 0.048
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Capacity development of existing farmer groups, WUG and RUG | 0.054
3. Construction of milk collection centers with chilling facilities | 1.5
3. Retraining on livestock husbandry | 0.156
3. Retraining on vegetable production techniques | 1.13
3. Shed construction | 1.1009
4. Chopping machine (for dairy groups) | 0.663
4. Equipment dairy production groups | 1.04
4. Poultry for farm resilience and diversification | 0.225
4. Training in packaging & handling | 1.54
4. Training on clean milk production | 0.078
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.08
5. Retraining on clean milk production | 0.104
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.208
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Training on farm record keeping | 0.26
7. Retraining on farm record keeping | 0.26
7. Workshops (planning, review, evaluation) | 0.025
9. Biogas digester | 0.45
MONGAR DZONGKHAG | 27.348
1. Awareness & Mobilization | 0.788
1. Milk cans | 0.645
1. Perenial fodder in fallow and marginal land | 0.14
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 2.79
2. Training on livestock husbandry | 0.338
2. Training on vegetable production techniques | 0.563
2. Water efficient irrigation | 1
2. Water Users Associations (O&M) | 0.028
2. Winter fodder crop demonstration and seed supply | 0.08
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Construction of milk collection centers with chilling facilities | 1.5
3. Retraining on livestock husbandry | 0.286
3. Retraining on vegetable production techniques | 1.63
3. Shed construction | 1.386
4. Chopping machine (for dairy groups) | 1.69
4. Equipment dairy production groups | 0.78
4. Poultry for farm resilience and diversification | 0.225
4. Training in packaging & handling | 3.03
4. Training on clean milk production | 0.234
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.14
5. Renovation of irrigation infrastructure | 5
5. Retraining on clean milk production | 0.286
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.416
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Milk analyzer | 0.106
6. Training on farm record keeping | 0.442
7. Workshops (planning, review, evaluation) | 0.025
9. Biogas digester | 1.5
OPM | 61.51
1. Coordination meetings with dzongkhags | 0.65
1. Developemnt of extension materials | 3.9
1. Development of business model and sustainability plan for service and O&M | 0.163
1. District engineers and extension agents (design and construction) | 0.767
1. Multistakeholders facilitation process | 2.515
1. National/External TA | 3
1. Pay & allowances for OPM staff | 3.043
1. Printing and publications | 0.12
1. Training on gender | 0.15
1. Vehicle operation and Maintenance | 0.5
2. Attend annual Governing council meeting at Rome, Italy | 0.3
2. Maintenance of Building | 0.5
2. Pay & allowance for Contract staff | 0.779
2. Pay & allowances for 2 Liaison staff | 0.74
2. Programme Supervision Mission | 0.905
2. Training on knowledge management | 0.25
3. Annual outcome surveys | 1.3
3. Capacity development for CARLEP Stakeholders | 4
3. Maintenance of Equipment | 0.1
3. Small post-harvest equipments | 15.552
3. Training on marketing & value-chain | 8.075
3. Training on monitoring and evaluation | 0.75
3. Training on report writing documentation and information sharing | 0.3
4. Information management dessimination | 0.2
4. Mid-term review | 1.95
4. Scanner | 0.1
4. Training on financial management | 1.2
4. Updating of O&M models for irrigation and farm roads | 0.39
4. Utilities - telephone, internet, electricity, water, fax, sewarage, post, etc. | 0.502
4. Workshops and meetings | 2.016
5. Office supplies | 0.198
6. Office equipment | 0.5
6. Travel | 2.058
7. Others | 0.437
9. Biogas digester | 3.6
PEMAGATSHEL DZONGKHAG | 18.156
1. Awareness & Mobilization | 0.593
1. Construction of milk collection sheds | 0.585
1. Milk cans | 0.3
1. Perenial fodder in fallow and marginal land | 0.14
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 1.395
2. Training on livestock husbandry | 0.195
2. Training on vegetable production techniques | 0.563
2. Upgrading of farm roads to climate resilient standards | 1.083
2. Water efficient irrigation | 1
2. Winter fodder crop demonstration and seed supply | 0.096
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Capacity development of existing farmer groups, WUG and RUG | 0.054
3. Construction of milk collection centers with chilling facilities | 1.5
3. Retraining on livestock husbandry | 0.13
3. Retraining on vegetable production techniques | 1.3
3. Shed construction | 0.924
4. Chopping machine (for dairy groups) | 0.845
4. Equipment dairy production groups | 0.65
4. Poultry for farm resilience and diversification | 0.15
4. Training in packaging & handling | 0.2
4. Training on clean milk production | 0.156
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.2
5. Retraining on clean milk production | 0.13
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.26
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Training on farm record keeping | 0.13
7. Milk processing unit | 2.34
7. Retraining on farm record keeping | 0.312
7. Workshops (planning, review, evaluation) | 0.025
9. Biogas digester | 0.6
RAMCO | 26.902
1. Awareness on marketing groups | 1
1. Business plan-based planning of market infrastructure | 1
1. Development of training packages for agriculture entrepreneurs | 0.65
1. Formation of vegetable marketing groups | 1.625
1. Multi-stakeholder platforms and network development | 1
1. Other Trainings to Groups, Cooperatives & Entrepreneurs | 3.7
1. Strengthening of the DAMC market information system | 1.508
2. Formation of dairy marketing groups | 1.3
2. Strengthening of existing marketing and cooperative capacity development packages | 0.5
2. Value-chain infrastructure | 7
3. Improve existing marketing and market channel in capacity development packages | 4
1. Value-chain equipment | 1.5
2. Equipment related to Market Information System upgrade | 2.119
RLDC KANGLUNG | 36.022
1. CAHW model development and packaging | 0.975
1. Development of training materials | 1.3
1. Development of training packages for agriculture entrepreneurs | 0.65
2. Equipments for milk collection shed | 0.13
2. Training of extension agents | 1.2
2. Training of trainers (ToT) | 0.65
3. Construction of milk collection centers with chilling facilities | 6.24
3. Development of training material and field manuals | 0.245
3. Training of CAHWs | 0.54
3. Training of feed producers | 0.16
4. Bee Keeping | 0.3
4. Equipment dairy production groups | 3.3
4. Milk chillers | 0.9
4. Retraining of CAHWs | 0.54
4. Training in packaging & handling | 1.075
5. Milk quality test equipment | 0.078
6. Milk analyzer | 0.429
6. Transport facilities for CAHWs | 1.95
7. Milk processing unit | 4.68
7. Stipend for CAHWs | 1.463
8. Milk processing equipment | 4.4
9. Milk chilling tanker | 4.817
SAMDRUP JONGKHAR DZONGKHAG | 23.978
1. Awareness & Mobilization | 0.398
1. Construction of milk collection sheds | 1.7
1. Milk cans | 0.5
1. Perenial fodder in fallow and marginal land | 0.14
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 2.093
2. Training on livestock husbandry | 0.13
2. Training on vegetable production techniques | 0.563
2. Water efficient irrigation | 1
2. Water Users Associations (O&M) | 0.028
2. Winter fodder crop demonstration and seed supply | 0.096
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Construction of milk collection centers with chilling facilities | 2
3. Retraining on livestock husbandry | 0.234
3. Retraining on vegetable production techniques | 1.458
3. Shed construction | 1.386
4. Bee Keeping | 0.45
4. Chopping machine (for dairy groups) | 2.197
4. Equipment dairy production groups | 0.7
4. Poultry for farm resilience and diversification | 0.15
4. Training in packaging & handling | 0.505
4. Training on clean milk production | 0.195
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.2
5. Renovation of irrigation infrastructure | 4
5. Retraining on clean milk production | 0.13
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.26
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Training on farm record keeping | 0.26
7. Retraining on farm record keeping | 0.13
7. Workshops (planning, review, evaluation) | 0.025
9. Biogas digester | 0.75
TRASHI YANGTSE DZONGKHAG | 12.692
1. Awareness & Mobilization | 0.983
1. Construction of milk collection sheds | 0.3
1. Milk cans | 0.12
1. Perenial fodder in fallow and marginal land | 0.14
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 1.395
2. Training on livestock husbandry | 0.325
2. Training on vegetable production techniques | 0.563
2. Upgrading of farm roads to climate resilient standards | 1.083
2. Water efficient irrigation | 1.5
2. Winter fodder crop demonstration and seed supply | 0.048
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Capacity development of existing farmer groups, WUG and RUG | 0.054
3. Retraining on livestock husbandry | 0.078
3. Retraining on vegetable production techniques | 0.813
3. Shed construction | 0.616
4. Chopping machine (for dairy groups) | 0.172
4. Equipment dairy production groups | 0.13
4. Poultry for farm resilience and diversification | 0.15
4. Training in packaging & handling | 1
4. Training on clean milk production | 0.117
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.04
5. Retraining on clean milk production | 0.13
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.2
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Training on farm record keeping | 0.13
7. Retraining on farm record keeping | 0.13
7. Workshops (planning, review, evaluation) | 0.025
9. Biogas digester | 0.15
TRASHIGANG DZONGKHAG | 21.578
1. Awareness & Mobilization | 0.593
1. Milk cans | 0.6
1. Perenial fodder in fallow and marginal land | 0.14
1. Provision of stress tolorent vegetable seeds | 0.27
1. Upgrading of existing farmer groups | 0.043
2. Cross-breed cattle | 2.093
2. Training on livestock husbandry | 0.325
2. Training on vegetable production techniques | 0.563
2. Water efficient irrigation | 1
2. Water Users Associations (O&M) | 0.028
2. Winter fodder crop demonstration and seed supply | 0.08
3. Agricultural inputs for farm resilience and diversification | 0.216
3. Retraining on livestock husbandry | 0.26
3. Retraining on vegetable production techniques | 1.3
3. Shed construction | 1.386
4. Chopping machine (for dairy groups) | 1.69
4. Equipment dairy production groups | 1.04
4. Poultry for farm resilience and diversification | 0.15
4. Training in packaging & handling | 0.101
4. Training on clean milk production | 0.312
4. Training on post-harvest management | 0.558
5. Piggery for farm resilience and diversification | 0.1
5. Renovation of irrigation infrastructure | 5
5. Retraining on clean milk production | 0.312
5. Retraining on post-harvest management | 0.704
5. Training on use of crop residues and feed/fodder | 0.416
5. Up-scaling of Lead Farmer Training Model | 0.182
6. Exchange visits for farmers | 0.18
6. Farmer field festivals | 0.147
6. Training on farm record keeping | 0.13
7. Retraining on farm record keeping | 0.13
7. Workshops (planning, review, evaluation) | 0.029
9. Biogas digester | 1.5
Grand Total | 327.1759

## AGENCY_ACTIVITY (2)
AGENCY | OPM
Row Labels | Sum of PROPOSED BUDGET (AWPB)
1. Coordination meetings with dzongkhags | 0.65
1. Developemnt of extension materials | 3.9
1. Development of business model and sustainability plan for service and O&M | 0.163 | 10.425
1. District engineers and extension agents (design and construction) | 0.767
1. Multistakeholders facilitation process | 2.515
1. National/External TA | 3
1. Pay & allowances for OPM staff | 3.043
1. Printing and publications | 0.12
1. Training on gender | 0.15
1. Vehicle operation and Maintenance | 0.5
2. Attend annual Governing council meeting at Rome, Italy | 0.3
2. Maintenance of Building | 0.5
2. Pay & allowance for Contract staff | 0.779
2. Pay & allowances for 2 Liaison staff | 0.74
2. Programme Supervision Mission | 0.905
2. Training on knowledge management | 0.25
3. Annual outcome surveys | 1.3
3. Capacity development for CARLEP Stakeholders | 4
3. Maintenance of Equipment | 0.1
3. Small post-harvest equipments | 15.552
3. Training on marketing & value-chain | 8.075
3. Training on monitoring and evaluation | 0.75
3. Training on report writing documentation and information sharing | 0.3
4. Information management dessimination | 0.2
4. Mid-term review | 1.95
4. Scanner | 0.1
4. Training on financial management | 1.2
4. Updating of O&M models for irrigation and farm roads | 0.39
4. Utilities - telephone, internet, electricity, water, fax, sewarage, post, etc. | 0.502
4. Workshops and meetings | 2.016
5. Office supplies | 0.198
6. Office equipment | 0.5
6. Travel | 2.058
7. Others | 0.437
9. Biogas digester | 3.6
Grand Total | 61.51