## Works
[5 empty] | BASIC DATA | [6 empty] | Bid Document |  | Bidding Period |  | Bid Evaluation |  | Contract Evaluation
AWPB ACTIVITY CODE | Component/Activity/Sub-activity | Description | Implementing Agency | Lot No. | Issue # of Invitation of Bid | Lumpsum or BOQ | Procurement Method | Estimated Amount in BTN (million) | Pre or Post Qualification | Prior or Post Review | Plan Vs Actual | Date proposed | Date No objection | Bid Invitation Date | Bid opening-closing | Bid evaluation report | No objection | Contract amount in BTN (million) | Date contract award | Date contract signature | Beneficiary Contribution | Remarks
1.1.E.6 | Pilot irrigation schemes | Execute lift irrigation in four pilot sites based on feasibility study. | ARDC Wengkhar | 1 |  | BoQ | NCB | 21.2 |  | Prior | Plan | 15th Sept, 2018 | 20 th Sept, 2018 | 25th October, 2018 | 26th Nov, 2018 | 2018-12-10 | 15th Dec 2018 |  | 20th Dec, 2018 | 20th Dec, 2018 |  | To be verified for climate proofing and make appropriate changes in July and Auguts 2018
1.1.E.6 | Pilot irrigation schemes | Execute lift irrigation in four pilot sites based on feasibility study. | ARDC Wengkhar | [7 empty] | Actual
2.3.B.2 | Construction of Value-chain infrastructure | Market infrastrucure to be developed based on the need of MSP | RAMCO |  | August | BOQ | NCB | 7 | Pre | Prior | Plan | 10th Aug | 20th Aug | 25th Aug | 30th Sept | 10th Oct | 20th Oct |  | 1st Nov | 15th Nov
2.3.B.2 | Construction of Value-chain infrastructure | Market infrastrucure to be developed based on the need of MSP | RAMCO | [7 empty] | Actual
1.2.D.2 | Water efficient irrigation | Construction of 1.5 km pipe line and water reservior tank at Thonglingbi URS commercial site under Jarey gewog. | Lhuentse Agri. Sector | 1 |  | BOQ | NCB | 1.4 |  | prior | Plan | 30th July | 5th August | 10th August | 10th Sep | 21st Oct | 25th Oct
1.2.D.2 | Water efficient irrigation | Construction of 1.5 km pipe line and water reservior tank at Thonglingbi URS commercial site under Jarey gewog. | Lhuentse Agri. Sector | [7 empty] | Actual
1.1.F.2 | Upgrading of farm roads to climate resilient standards | Upgradation of 2km Jagorbi, URC farm road under Maedtsho gewog to climate relilient | Lhuentse Agri. Sector | 1 |  | BOQ | NCB | 1.08 |  | prior | Plan | 30th July | 5th August | 10th August | 10th Sep | 21st Oct | 25th Oct
1.1.F.2 | Upgrading of farm roads to climate resilient standards | Upgradation of 2km Jagorbi, URC farm road under Maedtsho gewog to climate relilient | Lhuentse Agri. Sector | [7 empty] | Actual
1.1.E.5 | Renovation of irrigation infrastructure | 5 km Yayung Irrigation Channel renovation with cammand area of 70 acres, 58 houeholds | Mongar Agri. Sector | 1 | 25th July 2018 | BoQ | NCB | 5 | prior | prior | Plan | 10th Aug. 2018 |  | 10th Oct. 2018 | 20th Oct. 2018 | 5th Nov. 2018 | 15th Nov. 2018 |  | 25th Nov. 2018 | 25th Nov. 20128 |  | Climate resilience
1.1.E.5 | Renovation of irrigation infrastructure | 5 km Yayung Irrigation Channel renovation with cammand area of 70 acres, 58 houeholds | Mongar Agri. Sector | [7 empty] | Actual
1.1.F.2 | Upgrading of farm roads to climate resilient standards | upgrading 5km Bartseri farm road based on climate resiient standards | Pemagatshel Agri. Sector | 1 |  | BOQ | NCB | 1.083 |  | Prior | Plan | 15th July 2018 | 20th July 2018 | 25th july 2018 | 24th Aug 2018 | 24th Sept 2018 | 30th Sept 2018 |  | 10th Oct 2018 | 10th Oct 2018 |  | Climate resilient expert will make a visit prior to bid proposal
1.1.F.2 | Upgrading of farm roads to climate resilient standards | upgrading 5km Bartseri farm road based on climate resiient standards | Pemagatshel Agri. Sector | [7 empty] | Actual
1.1.E.2.5 | Renovation of irrigation infrastructure | Renovation of irrigation infractructure at Aguruthang (Langchenphu) | S/Jongkhar Agri. sector | 1 |  | BOQ | NCB | 4.2 |  | Prior | Plan | 15 th August 2018 | 20th August 2018 | 21st August 2018 | 22nd sept 2018 |  | 29th Oct 2018 |  | 1st week of November 2018 | 1st week of November 2018
1.1.E.2.5 | Renovation of irrigation infrastructure | Renovation of irrigation infractructure at Aguruthang (Langchenphu) | S/Jongkhar Agri. sector | [7 empty] | Actual
1.1.E.5 | Irrigation Infrastructure | Renovation of 5 KM Upper Kangpar irrigation scheme | Trashigang Agri. Sector | 1 |  | BOQ | NCB | 4.5 |  | prior | Plan | 30th July | 5th August | 10th Aug | 10th Sep | 21st Oct | 25th Oct
1.1.E.5 | Irrigation Infrastructure | Renovation of 5 KM Upper Kangpar irrigation scheme | Trashigang Agri. Sector | [7 empty] | Actual
1.1.E.5 | Irrigation Infrastructure | Renovation of 1.5 KM Zengthi irrigation scheme | Trashigang Agri. Sector | 1 |  | BOQ | NCB | 0.5 |  | prior | Plan | 30th July | 5th August | 10th Aug | 10th Sep | 21st Oct | 25th Oct
1.1.E.5 | Irrigation Infrastructure | Renovation of 1.5 KM Zengthi irrigation scheme | Trashigang Agri. Sector | [7 empty] | Actual
1.2.D.2 | Water Efficient irrigation | Construction of water reservoir at Tsenkharla, Khamdang Gewog | Trashiyangtse Agri. Sector | 1 |  | BOQ | NCB | 1.5 |  | Prior | Plan | 15th August 2018 | 20th August 2018 | 21st August 2018 | 22nd Sept 2018 | 23rd Oct 2018 | 29th Oct 2018 |  | 8th Nov 2018 | 8th Nov 2018 |  | To be verified for climate proofing
1.2.D.2 | Water Efficient irrigation | Construction of water reservoir at Tsenkharla, Khamdang Gewog | Trashiyangtse Agri. Sector | [7 empty] | Actual
1.1.F.2 | Upgrading of farm roads to climate resilient standards | Improving of Karmazom farm road with climate resilient features | Trashiyangtse Agri. Sector | 1 |  | BOQ | NCB | 1.13 |  | Prior | Plan | 15th August 2018 | 20th August 2018 | 21st August 2018 | 22nd Sept 2018 | 23rd Oct 2018 | 29th Oct 2018 |  | 8th Nov 2018 | 8th Nov 2018 |  | To be verified for climate proofing
1.1.F.2 | Upgrading of farm roads to climate resilient standards | Improving of Karmazom farm road with climate resilient features | Trashiyangtse Agri. Sector | [7 empty] | Actual
2.3.C.1 | Construction of milk collection sheds | Construction of collection centre (MCC) | Lhuentse Liv. Sector | 1 |  | BOQ | NCB | 0.51 |  | Prior | Plan | 1st July 2018 | 10th July 2018 | 15th Aug. 18 | 15th Sept. 18 | 20th Sept. 18 | 20th Oct. 18
2.3.C.1 | Construction of milk collection sheds | Construction of collection centre (MCC) | Lhuentse Liv. Sector | [7 empty] | Actual
2.3.C.3 | Construction of milk collection centre with chilling facilities | Construction of MPU at Tangmachu | Lhuentse Liv. Sector | 1 |  | BOQ | NCB | 1.5 |  | Prior | Plan | 1st July 2018 | 10th July 2018 | 15th Aug. 18 | 15th Sept. 18 | 20th Sept. 18 | 20th Oct. 18
2.3.C.3 | Construction of milk collection centre with chilling facilities | Construction of MPU at Tangmachu | Lhuentse Liv. Sector | [7 empty] | Actual
2.3.C.3 | Construction of milk collection centers with chilling facilities |  | Mongar Liv. Sector | 1 |  | BoQ | NCB | 1.5 |  | Prior | Plan | 1st Week of August | 2nd Week of August | 3rd Week of August | 3rd Week of Sept. | 3rd Week of Sept. | 4th Week of Sept.
2.3.C.3 | Construction of milk collection centers with chilling facilities |  | Mongar Liv. Sector | [7 empty] | Actual
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Khar | Pemagatshel Liv. Sector | 1 |  | Lumpsum | Direct contract | 0.195 |  | Post | Plan | [10 empty] | Work to be awarded to Community Contract
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Khar | Pemagatshel Liv. Sector | [7 empty] | Actual
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Norboogang | Pemagatshel Liv. Sector | 2 |  | Lumpsum | Direct contract | 0.195 |  | post | Plan | [10 empty] | Work to be awarded to Community Contract
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Norboogang | Pemagatshel Liv. Sector | [7 empty] | Actual
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Yurung | Pemagatshel Liv. Sector | 3 |  | Lumpsum | Direct contract | 0.195 |  | post | Plan | [10 empty] | Work to be awarded to Community Contract
2.3.C.1 | Construction of milk collection sheds | Construct 1 no. milk collection shed at Yurung | Pemagatshel Liv. Sector | [7 empty] | Actual
2.3.C.3 | Construction of milk collection centers with chilling facilities | Construc 1 no. of milk collection centers with chilling facilities at Nanong | Pemagatshel Liv. Sector |  |  | BOQ | NCB | 1.5 |  | Prior | Plan | 5th September |  | 1st October | 1st November | 15th November
2.3.C.3 | Construction of milk collection centers with chilling facilities | Construc 1 no. of milk collection centers with chilling facilities at Nanong | Pemagatshel Liv. Sector | [7 empty] | Actual
2.3.C.7 | Milk processing unit | Construct 1 no. Milk Processing Unit at Nganglam | Pemagatshel Liv. Sector |  |  | BOQ | NCB | 2.34 |  | Prior | Plan | 5th September |  | 1st October | 1st november | 15th November
2.3.C.7 | Milk processing unit | Construct 1 no. Milk Processing Unit at Nganglam | Pemagatshel Liv. Sector | [7 empty] | Actual
2.3.C.1 | Construction of milk collection sheds | COnstruction of ten (10) milk collection sheds at various locations in the areas of dairy farmers group. The MCS will be cosntructed in Gomdar, Orong, Langchenphu, Martshala and Wangphu gewogs. | S/Jongkhar Liv. sector |  |  | Lumpsum | NCB | 1.7 | Post | prior | Plan | [9 empty] | stones, wooden materials and labour
2.3.C.1 | Construction of milk collection sheds | COnstruction of ten (10) milk collection sheds at various locations in the areas of dairy farmers group. The MCS will be cosntructed in Gomdar, Orong, Langchenphu, Martshala and Wangphu gewogs. | [8 empty] | Actual
2.3.C.3 | Construction of milk collection centers with chilling facilities | Construction of two (2) milk collection centres with chillinig facilities in Minjigang and Martang villages of Phuntshothang and Dewathang gewogs respectively | S/Jongkhar Liv. sector | 1 |  | Lumpsum | NCB | 1.52 | Post | Prior | Plan | [9 empty] | labour, wooden materials and stones
2.3.C.3 | Construction of milk collection centers with chilling facilities | Construction of two (2) milk collection centres with chillinig facilities in Minjigang and Martang villages of Phuntshothang and Dewathang gewogs respectively | [8 empty] | Actual

## Goods & inputs
PROCUREMENT PLAN FOR GOODS, INPUTS, MATERIALS & EQUIPMENTS
| Country/Organization | : BHUTAN | [5 empty] | FOR THE PERIOD JULY 2018- JUNE 2019
| Project/Program | : Commercial Agriculture and Resilient Livelihoods Enhancement Programme
| IFAD Loan No.: 2000000627 | IFAD Grant No. : 2000000838 | ASAP Grant No. : 2000000872
[5 empty] | BASIC DATA | [5 empty] | Bid Document |  | Bidding Period |  | Bid Evaluation |  |  | Contract Evaluation
AWPB CODE | Component/Activity/Sub-activity | Description | Implementing Agency | Lot No. | Issue # of Invitation of Bid | Estimated Amount in BTN (million) | Procurement Method | Pre or Post Qualification | Prior or Post Review | Plan Vs Actual | Date proposed | Date No objection | Bid Invitation Date | Bid opening-closing | Bid evaluation report | No objection | No objection for draft purchase order | Contract amount in US$ (000) | Date contract award | Date contract signature | Beneficiary Contribution | Remarks
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (1 Vertical autoclave 1000 L Capacity, 2000 Heat resistant plastic bottles, 2 wood moisture meter, 1 Mini autoclave 15 L capacity, 3 Infra-red thermometer) | ARDC Wengkhar | 1 |  | 1.25 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (1 Vertical autoclave 1000 L Capacity, 2000 Heat resistant plastic bottles, 2 wood moisture meter, 1 Mini autoclave 15 L capacity, 3 Infra-red thermometer) | [7 empty] | Actual
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (1 Saw dust mixing machine, 1 sawdust screening machine, 6 air compressor, 12 sets carbon coated drill bit, 1 infrared moisture determination FD 610-1) | ARDC Wengkhar | 2 |  | 1.25 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (1 Saw dust mixing machine, 1 sawdust screening machine, 6 air compressor, 12 sets carbon coated drill bit, 1 infrared moisture determination FD 610-1) | [7 empty] | Actual
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (2 Drill 12000 rpm Korean made, 1 analytical balance, 24 automatic spawn injector, 2 deep freezer temperature range -20 to -80oC) | ARDC Wengkhar | 3 |  | 1.25 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Purchase of materials and equipment required for mushroom spawn and promotion (2 Drill 12000 rpm Korean made, 1 analytical balance, 24 automatic spawn injector, 2 deep freezer temperature range -20 to -80oC) | [7 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kg of Quinoa seeds | ARDC Wengkhar | 1 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from ommunity based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kg of Quinoa seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 50 kg of vegetable seeds (Cole crops) | ARDC Wengkhar | 2 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre, One Stop Farmers Shop and Vegetable Seed Growers based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 50 kg of vegetable seeds (Cole crops) | ARDC Wengkhar | [6 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kgs of Quinoa seeds | ARDC Wengkhar | 3 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from community based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kgs of Quinoa seeds | [7 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 20 kg of Chilli seeds | ARDC Wengkhar | 4 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre, One Stop Farmers Shop and Vegetable Seed Growers based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 20 kg of Chilli seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 52 kgs of Onion seeds | ARDC Wengkhar | 5 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre, One Stop Farmers Shop and Vegetable Seed Growers based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 52 kgs of Onion seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kgs of Quinoa seeds | ARDC Wengkhar | 6 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from community based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 1300 kgs of Quinoa seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 52 kgs of Onion seeds | ARDC Wengkhar | 7 |  | 0.129 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre, One Stop Farmers Shop and Vegetable Seed Growers based on the government approved rate.
1.1.A.9 | Crop diversification (Cereal, oil seeds, pulses and fruits) | Purchase of 52 kgs of Onion seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.1 | Farm level rainwater harvesting infrastructure | Purchase of rainwater harvesting materials (60 bundles of HDPE pipes, 4 nos. of sintex tank and other accessories) | ARDC Wengkhar | 1 |  | 0.8 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.B.1 | Farm level rainwater harvesting infrastructure | Purchase of rainwater harvesting materials (60 bundles of HDPE pipes, 4 nos. of sintex tank and other accessories) | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Purchase of 1000 kg of Rajma beans seeds | ARDC Wengkhar | 1 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre or One Stop Farmers Shop or Community based on the government approved rate.
1.1.B.2 | Seeds and seedlings | Purchase of 1000 kg of Rajma beans seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Collection and purchase of 750 kgs of traditional chilli varieties from different locations to extract seeds | ARDC Wengkhar | 2 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase of traditional chilli varieties from different chilli growing areas to extract seeds, process, package and used for research purpose or distribute to CS Villages.
1.1.B.2 | Seeds and seedlings | Collection and purchase of 750 kgs of traditional chilli varieties from different locations to extract seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Collection and purchase of 500 kgs of oher traditional vegetables (Cucurbits and beans) to extract seeds | ARDC Wengkhar | 3 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase of traditional cucurbit varieties from different cucurbit growing areas to extract seeds, process, package and used for research purpose or distribute to CS Villages.
1.1.B.2 | Seeds and seedlings | Collection and purchase of 500 kgs of oher traditional vegetables (Cucurbits and beans) to extract seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Purchase of 5 kgs of heat tolerant cabbage seeds | ARDC Wengkhar | 4 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre or from India based on the government approved rate.
1.1.B.2 | Seeds and seedlings | Purchase of 5 kgs of heat tolerant cabbage seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Purchase of 5 Kgs of heat tolerant radish seeds | ARDC Wengkhar | 5 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre or from India based on the government approved rate.
1.1.B.2 | Seeds and seedlings | Purchase of 5 Kgs of heat tolerant radish seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.2 | Seeds and seedlings | Purchase of 5 kgs of heat tolerant cauliflower seeds | ARDC Wengkhar | 6 |  | 0.125 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Direct purchase from National Seed Centre or from India based on the government approved rate.
1.1.B.2 | Seeds and seedlings | Purchase of 5 kgs of heat tolerant cauliflower seeds | ARDC Wengkhar | [6 empty] | Actual
1.1.B.3 | Tools for permaculture | Purchase of water use efficient irrigation materials (30 rolls each of 25 mm, 30 mm and 50 mm HDPE pipes) | ARDC Wengkhar | 1 |  | 0.583 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.B.3 | Tools for permaculture | Purchase of water use efficient irrigation materials (30 rolls each of 25 mm, 30 mm and 50 mm HDPE pipes) | ARDC Wengkhar | [6 empty] | Actual
1.1.B.3 | Tools for permaculture | Purchase of 50 sets of drippers, sprinklers and other accessories | ARDC Wengkhar | 2 |  | 0.583 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.B.3 | Tools for permaculture | Purchase of 50 sets of drippers, sprinklers and other accessories | ARDC Wengkhar | [6 empty] | Actual
1.1.B.3 | Tools for permaculture | Purchase of pruning shears, garden rake, mulching plastic, labelling materials, poly pot and low cost polyhouse set | ARDC Wengkhar | 3 |  | 0.583 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.B.3 | Tools for permaculture | Purchase of pruning shears, garden rake, mulching plastic, labelling materials, poly pot and low cost polyhouse set | ARDC Wengkhar | [6 empty] | Actual
1.1.D.9 | Demonstration inputs for lead farmers | Purchase of 40 sets of demonstration inputs for Lead Farmers (farm tools) and 200 pkts of vegetable seeds, meet expenses for on-farm demo plots and 0.300 m allocation for SJI to meet expenses for lead farmer expansion in SJ | ARDC Wengkhar | 1 |  | 1 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.D.9 | Demonstration inputs for lead farmers | Purchase of 40 sets of demonstration inputs for Lead Farmers (farm tools) and 200 pkts of vegetable seeds, meet expenses for on-farm demo plots and 0.300 m allocation for SJI to meet expenses for lead farmer expansion in SJ | ARDC Wengkhar | [6 empty] | Actual
1.1.D.9 | Production inputs | Purchase of 200 pkts of vegetable seeds, 100 kgs plastic mulch and 500 kg polytube materials | ARDC Wengkhar | 2 |  | 0.4 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.D.9 | Production inputs | Purchase of 200 pkts of vegetable seeds, 100 kgs plastic mulch and 500 kg polytube materials | ARDC Wengkhar | [6 empty] | Actual
1.1.D.10 | Poly-tunnels | Purchase of 40 sets of greenhouse plastic and film band | ARDC Wengkhar | 1 |  | 0.5 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.D.10 | Poly-tunnels | Purchase of 40 sets of greenhouse plastic and film band | ARDC Wengkhar | [6 empty] | Actual
1.1.D.10 | Poly-tunnels | Purchase of 40 sets of greenhouse plastic and film band | ARDC Wengkhar | 2 |  | 0.3 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.1.D.10 | Poly-tunnels | Purchase of 40 sets of greenhouse plastic and film band | ARDC Wengkhar | [6 empty] | Actual
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 25 deep freezers (100 L capacity) for seed growers performing well and for seed conservation on station | ARDC Wengkhar | 1 |  | 0.525 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 25 deep freezers (100 L capacity) for seed growers performing well and for seed conservation on station | ARDC Wengkhar | [6 empty] | Actual
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 25 weighing balance (1 kg capacity) and seed packaging pouches of 3 different sizes | ARDC Wengkhar | 2 |  | 0.525 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 25 weighing balance (1 kg capacity) and seed packaging pouches of 3 different sizes | ARDC Wengkhar | [6 empty] | Actual
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of a labelling machine and accessories. | ARDC Wengkhar | 3 |  | 0.525 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of a labelling machine and accessories. | ARDC Wengkhar | [6 empty] | Actual
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 15 sets of greenhouse. | ARDC Wengkhar | 4 |  | 0.525 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.C.3 | Equipment and input support vegetable seed growers | Purchase of 15 sets of greenhouse. | ARDC Wengkhar | [6 empty] | Actual
1.2.D.3 | Small post-harvest equipments | Purchase of 10 sets of greenhouse to make Solar drier | ARDC Wengkhar | 1 |  | 0.6 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.D.3 | Small post-harvest equipments | Purchase of 10 sets of greenhouse to make Solar drier | ARDC Wengkhar | [6 empty] | Actual
1.2.D.3 | Small post-harvest equipments | Purchase of post harvest equipments (3 quinoa deshusking machine, 1 vegetable seed extraction machine, 10 nos.of exhaust fan, 10 nos. of pre-fabricated seed or farm produce drying trolley | ARDC Wengkhar | 2 |  | 1.2 | NCB |  | Post | Plan | 2018-05-15 | NA | 2018-06-15 | 2018-06-15 | 2018-07-03 | NA | NA | NA | 2018-07-05 | NA | NA | Purchase using the Annual Quotation as per the RGoB Procurement Rules
1.2.D.3 | Small post-harvest equipments | Purchase of post harvest equipments (3 quinoa deshusking machine, 1 vegetable seed extraction machine, 10 nos.of exhaust fan, 10 nos. of pre-fabricated seed or farm produce drying trolley | ARDC Wengkhar | [6 empty] | Actual
1.3.E.6 | Equipment dairy production groups | Equipment dairy production groups (LN2 transport can, semen bank tank) | RLDC | 1 |  | 3.3 | NCB |  | Post | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018 | NA | NA
|  |  | RLDC | [6 empty] | Actual
2.3.C.2 | Equipment of milk collection sheds |  | RLDC | 1 |  | 0.13 | NCB |  | Post | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018
|  |  | RLDC | [6 empty] | Actual
2.3.C.4 | Milk chillers | Purchase of milk chillers | RLDC |  |  | 0.9 | NCB |  | Post | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018
|  |  | RLDC | [6 empty] | Actual
2.3.C.5 | Milk quality test equipment | Purchase of milk quality test equipments | RLDC |  |  | 0.078 | NCB |  | Post | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018
|  |  | RLDC | [6 empty] | Actual
2.3.C.6 | Milk analyzer | Purchase of milk analyzer | RLDC |  |  | 0.429 | NCB |  | Post | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018
|  |  | RLDC | [6 empty] | Actual
2.3.C.9 | Milk processing equipment | Purchase of Batch Pasturizer; 2 fermentation tank; | RLDC |  |  | 4.4 | NCB |  | Prior | Plan | 15th July 2018 | NA | 25th July 2018 | 25th August 2018 | 10th Sept. 2018 | [6 empty] | Revised on 30th August
|  |  | RLDC | [6 empty] | Actual
2.3.C.11 | Milk chilling tanker | Purchase of 2 milk tankers from STCBL | RLDC | 1 |  | 4.817 | Direct Purchase |  | Prior | Plan | 1st Oct. 2018 | 15th Oct. 2018 | 25th Oct. 2018 | 25th Nov. 2018 | 5th Dec. 2018 | 15th Dec. 2018
Actual
2.2.1.a.3 | Marketing and value addition equipment | Supply of marketing and value addation equipment to traders/vendors | RAMCO |  |  | 4 | NCB |  | Prior | Plan | 10th July |  | 20th July | 20th August | 27th August |  |  |  | 27th August |  |  | Budget was reappropriated from packaging and handling materials as recommended by CPM
Actual
2.3.B.1 | Value-chain equipments | Supply of equipments and materials required to operate market infrastructure | RAMCO |  |  | 1.5 | NCB |  | Post | Plan | 20th Oct |  | 30th Oct | 30th Nov | 7th Nov |  |  |  | 7th Nov |  |  | Budget will be used to procure material and equipment required for operating the infrastructure
Actual
3.1.A.2 | Equipment related to Market Information System upgrade | Purchase of MIS software (Database & statistical analysis package) and laptop/desktop/tablets | RAMCO |  |  | 2.119 | NCB |  | Post | Plan | 10th Nov |  | 30th Nov | 30th Dec | 10th Dec |  |  | 30th Dec | 10th Jan
Actual
2.3.B.1 | Value-chain equipments | Plastic Crates | FCBL |  |  | 1.1 | NCB | Post |  | Plan
Actual
1.1.A.3.a | Production inputs for farm resilience and diversification(Agriculture) | Purchase of 1000 kgs of quinoa seeds | Lhuentse Agri. Sector | 1 |  | 0.1 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | Direct from the farmers
Actual
1.1.A.3.b | Production inputs for farm resilience and diversification(Agriculture) | Purchase of 1700 ks of Mungbean/Rajma bean seed | Lhuentse Agri. Sector | 2 |  | 0.116 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | Direct from the farmers
Actual
1.2.D.1 | Provision of stress tolorent vegetable seeds | Purchase of 3700 pkts ofwinter vegetable seeds | Lhuentse Agri. Sector | 1 |  | 0.11 | NCB |  | post | Plan | [11 empty] | Purchase from NSC, Bhutan Alpine seeds, ASSR etc
Actual
1.2.D.1.1 | Provision of stress tolorent vegetable seeds | Purchase of 3330 pkts of summer vegetable seeds | Lhuentse Agri. Sector | 2 |  | 0.1 | NCB |  | post | Plan | [11 empty] | Purchase from NSC, Bhutan Alpine seeds, ASSR etc
Actual
1.2.D.1.2 | Provision of stress tolorent vegetable seeds | Purchase 750 kgs of legume crops | Lhuentse Agri. Sector | 3 |  | 0.06 | NCB |  | post | Plan | [11 empty] | Purchase from NSC, Bhutan Alpine seeds, ASSR etc
Actual
1.2.D.3 | Water efficient irrigation | Purchase of Flexible pipes, water sprinklers, sintex tank for youths farmers. | Lhuentse Agri. Sector | 1 |  | 0.1 | NCB |  | Post | Plan | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | Purchase will be based on the quotation of Dzongkhag, DoA, Ministry ctc.
Actual
1.1.A.3 | Production inputs for farm resilience and diversification(Agriculture) | Procurement of assorted vegetables seeds - 3500 pkts in 2 lots - 1 for summer and 1 for winter with worth of Nu. 0.108 | Mongar Agri. Sector |  |  | 0.216 | NCB | post | post | Plan | 25th July 2018 |  | 10th Aug. 2018 | [8 empty] | To be supply 20th Aug. 2018 to farmers through direct purchase based on NSC rates
Actual
1.2.D.3 | Water efficient irrigation | Purchase of materials and equipments (Cement, pipes, MS rod, gravels, sand, wire, joints) | Mongar Agri. Sector |  |  | 1 | NCB | Post | Post | Plan | 5th July 2018 | 10th July 2018 | 20th Aug 2018 | 25 the Aug. 2018 | 10th July 2018 | 10th July 2018 | 25 th july 2018 | 30th July 2018 | 30th July 2018 | 30th July 2018
Actual
1.1.A.11.1 | Crop diversification(Cereals, oil seeds, pulses& fruits) | Procurement of 110 kgs of quinoa | Pemagatshel Agri. Sector | 1 |  | 0.011 | Shopping for Goods |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | procure locally
Actual
1.1.A.11.2 | Crop diversification(Cereals, oil seeds, pulses& fruits) | Procurement of 650 kgs of Hybrid maize | Pemagatshel Agri. Sector | 2 |  | 0.205 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | procure from NSC
Actual
1.2.D.1 | Provision of stress tolorent vegetable seeds | Procure stress tolarant assorted vegetable seeds | Pemagatshel Agri. Sector | 1 |  | 0.27 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | [7 empty] | Procure seeds from NSC in consultation with ARDC Wengkhar
Actual
1.2.D.3 | Water efficient irrigation | Procure sprinklers,drip,pipes,syntax tank | Pemagatshel Agri. Sector | 1 |  | 1 | NCB |  | Post | Plan | 15th July 2018 |  | 25th July 2018 | 24th August 2018 | 24th August 2018 |  |  |  | 11th September 2018 | 11 th September 2018
Actual
1.1.A.3.a | Production inputs for farm resilience and diversification(Agriculture) | Purchase of 400 kgs of mustard seeds | S/Jongkhar Agri. sector | 1 |  | 0.04 | Direct Purchase |  | Post | Plan | NA | [10 empty] | To be bought directly from farmer's field
| Production inputs for farm resilience and diversification(Agriculture) |  | S/Jongkhar Agri. sector | [6 empty] | Actual
1.1.A.3.b | Production inputs for farm resilience and diversification(Agriculture) | Purchese of 200 kgs of Quinoa | S/Jongkhar Agri. sector | 1 |  | 0.116 | Direct Purchase |  | Post | Plan | NA | [10 empty] | To be bought directly from farmer's field
| Production inputs for farm resilience and diversification(Agriculture) |  | S/Jongkhar Agri. sector | [6 empty] | Actual
1.1.A.3.c | Production inputs for farm resilience and diversification(Agriculture) | Purchase of 300 kgs of ground apple seeds | S/Jongkhar Agri. sector | 1 |  | 0.06 | Direct Purchese |  | Post | Plan | NA | [10 empty] | To be bought directly from farmer's field
| Production inputs for farm resilience and diversification(Agriculture) |  | S/Jongkhar Agri. sector | [6 empty] | Actual
1.1.D.2.1 | Production inputs | Supply of 19 Kgs of asorted vegetable seeds as multiple procurement throughout FY with <USD 2000/purchase | S/Jongkhar Agri. sector |  |  | 0.27 | Direct Purchese |  | Post | Plan | [11 empty] | To be bought directly from National Seed Center, Paro
|  |  | S/Jongkhar Agri. sector | [6 empty] | Actual
1.2.D.3 | Water efficient irrigation | Procure sprinklers,drip,pipes,syntax tank | S/Jongkhar Agri. sector | 1 |  | 1 | NCB |  | Post | Plan | 15th July 2018 |  | 25th July 2018 | 24th August 2018 | 24th August 2018 |  |  |  | 11th September 2018 | 11 th September 2018
Actual
1.1 A.3.a | Production inputs for farm resilience | Purchse of 1000 kgs of quinoa seeds | Trashigang Agri. Sector | 1 |  | 0.1 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Directly purchase from farmers
Actual
1.1 A 3.b | Production inputs for farm resilience | purchse of 1700 kgs of Mung bean seeds | Trashigang Agri. Sector | 2 |  | 0.116 | Shopping for Goods |  | Post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Directly purchase from farmers
Actual
1.2.D.1.a | Stress tolerant vegetable seeds | Purchase of winter vegetable seeeds | Trashigang Agri. Sector | 1 |  | 0.11 | Direct Purchase |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Purchase from National seed center
Actual
1.2.D.b | stree tolerant vegetable seeds | Purchase of cole crop seeds | Trashigang Agri. Sector | 2 |  | 0.06 | Shopping for Goods |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Purchase from National seed center
Actual
1.2.D.c | stree tolerant vegetable seeds | Purchase of summer vegetable seeds | Trashigang Agri. Sector | 3 |  | 0.1 | Shopping for Goods |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Purchase from National seed center
Actual
1.2.D.d | Water efficient irrigation | Purchase of flexible pipes, water sprinklers, Sintex tank | Trashigang Agri. Sector | 1 |  | 0.1 | NCB |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Purchase will be based on the quotation of Department of Agriculture. (Financial progress will be reflect in the works)
Actual
1.1.D.1 | Training of lead farmer modeling | Training of lead farmer modeling and input supply | Trashigang Agri. Sector | 1 |  | 0.182 | NCB |  | post | Plan | NA | NA | NA | NA | NA | NA | [5 empty] | Purchase of inputs will be based on Dzongkhag , DoA, Ministry's quotation
Actual
1.1 A.3.a | Production inputs for farm resilience | Purchase of 200 kgs of soyabean seeds | Trashiyangtse Agri. Sector | 1 |  | 0.072 | Direct Purchase |  | Post | Plan | [11 empty] | To be directly purchased from farmers fields.
Actual
1.1 A 3.b | Production inputs for farm resilience | Puchase of 200 kgs of groundnut seeds | Trashiyangtse Agri. Sector | 2 |  | 0.072 | Direct Purchase |  | Post | Plan | [11 empty] | To be directly purchased from farmers fields.
Actual
1.1 A 3.c | Production inputs for farm resilience | Purchase of 200 kgs of millet seeds | Trashiyangtse Agri. Sector | 3 |  | 0.072 | Direct Purchase |  | Post | Plan | [11 empty] | To be directly purchased from farmers fields.
Actual
1.2.D.1 |  | Purchase of stress tolerant 1500 pkds of vegetable seeds | Trashiyangtse Agri. Sector | 1 |  | 0.27 | Direct Purchase |  | Post | Plan | [11 empty] | To be directly purchased from National Seed Center, paro
Actual
1.2.D.3 |  | Purchase of water pipes, sprinklers, drip irrigation | Trashiyangtse Agri. Sector | 1 |  | 1.5 | Direct Purchase |  | Post | Plan | [11 empty] | Revised on 30th August
Actual
1.1.A.4.a | Production inputs for farm resilience and diversification | Purchase of poultry birds (10 birds each for 15 HH) | Lhuentse Liv. Sector | 1 |  | 0.038 | DP |  | Post | plan | NA | NA | NA | NA | NA | NA | [5 empty] | Directly purchase from farmers
Actual
1.1.A.4.b | Production inputs for farm resilience and diversification | Purchase of CGI Sheet | Lhuentse Liv. Sector | 2 |  | 0.058 | NCB |  | Post | plan | 1st JULY | NA | 15TH AUG | 15TH SEPT | 25th Sept
Actual
1.1.A.4.c | Production inputs for farm resilience and diversification | Purchase of Cement | Lhuentse Liv. Sector | 3 |  | 0.032 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept
Actual
1.1.A.4.d | Production inputs for farm resilience and diversification | Purchase of feed for birds | Lhuentse Liv. Sector | 4 |  | 0.1 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept
Actual
1.1.A.4.e | Production inputs for farm resilience and diversification | Transportation cost | Lhuentse Liv. Sector | 5 |  | 0.025 | DP |  | Post | plan
Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Piggery) | Purchase of native piglets (Three piglets each for two farms) | Lhuentse Liv. Sector | 1 |  | 0.04 | DP |  | Post | plan | [11 empty] | Directly purchase from farmers
Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Piggery) | Purchase of CGI Sheet | Lhuentse Liv. Sector | 2 |  | 0.024 | NCB |  | Post | plan | 1st JULY | NA | 15TH AUG | 15TH SEPT | 25th Sept
Actual
1.1.A.5.c | Production inputs for farm resilience and diversification (Piggery) | Purchase of Cement | Lhuentse Liv. Sector | 3 |  | 0.016 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept
Actual
1.3.D.1 | Perinial fodder in fallow and marginal land | Purchase of barbed wire | Lhuentse Liv. Sector | 1 |  | 0.127 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept
Actual
1.3.D.2 | Winter fodder crop demostration and seed supply) | Purchase of seed and seedlings | Lhuentse Liv. Sector | 1 |  | 0.48 | DP |  | Post | plan | [11 empty] | Directly purchase from National Seed Center
Actual
1.3.D.4 | Chopping machine for Dairy Groups) | Purchase of chopping machine | Lhuentse Liv. Sector | 1 |  | 0.51 | NCB |  | Post | plan | 1st JULY | NA | 15TH AUG | 15TH SEPT | 25th Sept | [6 empty] | Revised on 30th August
Actual
1.3.E.1 | Milk Cans | Purchase of Milk Can | Lhuentse Liv. Sector | 1 |  | 0.15 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept | [6 empty] | Revised on 30th August
Actual
1.3.D.4 | Shed Construction | Supply of Dairy shed materials | Lhuentse Liv. Sector | 1 |  | 1.101 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept | [6 empty] | Revised on 30th August
Actual
1.3.E.6 | Equipments dairy production group | Purchase of equipments | Lhuentse Liv. Sector | 1 |  | 1.04 | NCB |  | Post | plan | 1st JULY | NA | 15th AUG | 15th SEPT | 25th Sept | [6 empty] | Revised on 30th August
|  |  | Lhuentse Liv. Sector | [6 empty] | Actual
1.1.A.4.a | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of Native pullets (100 Nos) | Mongar Liv. Sector | 1 |  | 0.12 | Direct Purchase |  | post | Plan | [11 empty] | Farmers
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.1.A.4.b | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of CGI sheet/Cement/wire mash for 10 poutry sheds | Mongar Liv. Sector | 2 |  | 0.105 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | NA |  |  |  | 50% | Quatation
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase of Native piglets (10 Nos) | Mongar Liv. Sector | 1 |  | 0.07 | Direct Purchase |  | post | Plan | [11 empty] | Farmers
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase shed construction materials (cement/CGI sheet) for 5 piggery sheds) | Mongar Liv. Sector | 2 |  | 0.07 | NCB |  | Post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | NA |  |  |  | 50% | Quatation
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.D.1.a | Perenial fodder in fallow and marginal land | Purchase of Pasture seed &seedlings, (10Acres) lot -1 | Mongar Liv. Sector | 1 |  | 0.07 | Direct Purchase |  | Post | Plan | [11 empty] | National suplier
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.D.1.b | Perenial fodder in fallow and marginal land | Purchase of grass-slips, cuttings (10Acres) -2 | Mongar Liv. Sector | 2 |  | 0.07 | Direct Purchase |  | Post | Plan
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.D.2 | Winter fodder crop demonstration and seed supply | Purchase of Pasture seed &seedlings (12Acres) | Mongar Liv. Sector |  |  | 0.08 | Direct Purchase |  | post | Plan | [11 empty] | National suplier
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.D.4 | Chopping machine (for dairy groups) | Purchase of Grass/Fodder Chopping Machines (40) | Mongar Liv. Sector |  |  | 1.3 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | [6 empty] | Quatation
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.E.1 | Milk cans | Purchase Milk cans, Milk Buckets and sanitary items (120 Noss | Mongar Liv. Sector |  |  | 0.645 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | [6 empty] | Quatation
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.E.4.a | Shed construction | Purchase of CGI sheets and assoceries for hygenic dairy sheds | Mongar Liv. Sector |  |  | 0.63 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | [6 empty] | Quatation
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.E.4.b | Shed construction | Purchase of cement for hygenic dairy sheds | Mongar Liv. Sector |  |  | 0.63 | Direct Purchase |  | post | Plan | [11 empty] | Dz. Agent
|  |  | Mongar Liv. Sector | [6 empty] | Actual
1.3.E.6 | Equipment dairy production groups | Purchase of of equipments dairy production group | Mongar Liv. Sector |  |  | 1.04 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | [6 empty] | Quatation
Actual
1.1.A.4.a | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of CGI sheet, wiremesh (10 units of native poultry ) | Pemagatshel Liv. Sector | 1 |  | 0.085 | NCD |  | post | Plan
Actual
1.1.A.4.b | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of cement including transportation (10 units of native poultry ) | Pemagatshel Liv. Sector | 2 |  | 0.02 | Direct Purchase |  | post | Plan | [11 empty] | To be procured from Authorized cement agent
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.1.A.4.c | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of Pullets including transportation (10 units of native poultry ) | Pemagatshel Liv. Sector | 3 |  | 0.045 | Direct Purchase |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of CGI sheet (10 units of native piggery) | Pemagatshel Liv. Sector | 1 |  | 0.05 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of cement including transportation (10 units of native piggery) | Pemagatshel Liv. Sector | 2 |  | 0.05 | Direct Purchase |  | post | Plan | [11 empty] | To be procured from Authorized cement agent
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of piglets including transportation | Pemagatshel Liv. Sector | 3 |  | 0.1 | Direct Purchase |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.D.1.a | Perenial fodder in fallow and marginal land | Supply of temperate grass mixture seeds | Pemagatshel Liv. Sector | 1 |  | 0.07 | Direct purchase |  | post | Plan | [11 empty] | Seeds to be procured from National Seed Centre, Bumthang
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.D.1.b | Perenial fodder in fallow and marginal land | Supply of sub-tropical seeds | Pemagatshel Liv. Sector | 2 |  | 0.07 | Direct purchase |  | post | Plan | [11 empty] | do
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.D.2 | Winter fodder crop demonstration and seed supply | Procure and supply of oat seeds to dairy farmers | Pemagatshel Liv. Sector |  |  | 0.096 | Direct Purchase |  | Post | Plan | [10 empty] | Labour
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.D.4 | Chopping machine (for dairy groups) | Procure and supply of chopping machine (5 nos.) to dairy groups or farmers | Pemagatshel Liv. Sector |  |  | 0.65 | NCB |  | Post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.1 | Milk cans | Procure and supply of milk cans to dairy farmers | Pemagatshel Liv. Sector |  |  | 0.3 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.2 | Cross-breed cattle | Transportation charge for cross-breed cattle | Pemagatshel Liv. Sector |  |  | 0.12 | Direct Purchase |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.4 | Shed construction | Supply of CGI sheet (30 nos. of dairy sheds) | Pemagatshel Liv. Sector | 2 |  | 0.54 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.4 | Shed construction | Supply of cement including transportation (30 nos. of dairy sheds) | Pemagatshel Liv. Sector | 3 |  | 0.3 | Direct purchase |  | post | Plan | [11 empty] | To be procured from Authorized cement agent
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.a | Equipment dairy production groups | Supply of cream separators | Pemagatshel Liv. Sector |  |  | 0.12 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.b | Equipment dairy production groups | Supply of butter churners | Pemagatshel Liv. Sector |  |  | 0.12 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.c | Equipment dairy production groups | Supply of deep freezers | Pemagatshel Liv. Sector |  |  | 0.12 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.d | Equipment dairy production groups | Supply of display refrigerators | Pemagatshel Liv. Sector |  |  | 0.12 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.e | Equipment dairy production groups | Supply of alluminium pots | Pemagatshel Liv. Sector |  |  | 0.05 | NCB |  | post | Plan
|  |  | Pemagatshel Liv. Sector | [6 empty] | Actual
1.3.E.6.f | Equipment dairy production groups | Supply of milking buckets | Pemagatshel Liv. Sector |  |  | 0.12 | NCB |  | post | Plan
Actual
1.1.A.4.a | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of CGI sheet, wiremesh (10 units of native poultry ) | S/Jongkhar Liv. sector | 1 |  | 0.085 | Direct purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.A.4.b | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of cement including transportation (10 units of native poultry ) | S/Jongkhar Liv. sector | 2 |  | 0.02 | Direct Purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.A.4.c | Production inputs for farm resilience and diversification (Livestock - Poultry) | Supply of Pullets including transportation (10 units of native poultry ) | S/Jongkhar Liv. sector | 3 |  | 0.045 | Direct Purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of CGI sheet (10 units of native piggery in Gomdar, Martshala, Langchenphu and Pemathang) | S/Jongkhar Liv. sector | 1 |  | 0.05 | Direct purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of cement including transportation (10 units of native piggery) | S/Jongkhar Liv. sector | 2 |  | 0.05 | Direct Purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Livestock - Piggery) | Supply of piglets including transportation | S/Jongkhar Liv. sector | 3 |  | 0.1 | Direct Purchase |  | post | Plan
|  |  | S/Jongkhar Liv. sector | [6 empty] | Actual
1.1.B.5 | Bee Keeping | promote bee keeping by supplying materials and equipment (such as bee hives, brood boxes, casting machines, bee veils, etc) for bee keeping and train farmers of Pemathang, Phuntshothang and Langchenphu gewogs on it | S/Jongkhar Liv. sector |  |  | 0.45 | Direct | post | post | Plan | [11 empty] | Equipment will be directly purchased from the National Highland Development Research Centre, Bumthang as per their subsidy packages provisions.
Actual
1.1.B.12 | Biogas digester | COnstruction of bio gas digesters plants for the 30 farmer of Gomdar 8, Orong 4, Dewathang 4, Phuntshothang 4, Pemathang 4, Langchenphu 4, serthig 2 | S/Jongkhar Liv. sector |  |  | 0.75 | Direct | Post | Post | Plan
Actual
2.3.C.3.b | Construction of milk collection centers with chilling facilities | Procurement of chilling facilities (milk chillers) | S/Jongkhar Liv. sector | 1 |  | 0.48 | NCB |  | Post | Plan
Actual
1.1.A.4.a | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of Native pullets (100 Nos) | Trashigang Liv. Sector | 1 |  | 0.1 | Direct Purchase |  | post | Plan | [11 empty] | Farmers
Actual
1.1.A.4.b | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of CGI sheet/Cement/wire mash for 10 poutry sheds | Trashigang Liv. Sector | 2 |  | 0.05 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | NA |  |  |  | 50% | Quatation
Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase of Native piglets (10 Nos) | Trashigang Liv. Sector | 1 |  | 0.05 | Direct Purchase |  | post | Plan | [11 empty] | Farmers
Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase shed construction materials (cement/CGI sheet) for 5 piggery sheds) | Trashigang Liv. Sector | 2 |  | 0.05 | NCB |  | Post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | NA |  |  |  | 50% | Quatation
Actual
1.3.D.1.a | Perenial fodder in fallow and marginal land | Purchase of Pasture seed &seedlings, grass-slips, cuttings (10Acres) lot -1 | Trashigang Liv. Sector | 1 |  | 0.07 | Direct Purchase |  | Post | Plan | [11 empty] | National suplier
Actual
1.3.D.1.b | Perenial fodder in fallow and marginal land | Purchase of Pasture seed &seedlings, grass-slips, cuttings (10Acres) -2 | Trashigang Liv. Sector | 2 |  | 0.07 | Direct Purchase |  | Post | Plan
Actual
1.3.D.2 | Winter fodder crop demonstration and seed supply | Purchase of Pasture seed &seedlings (12Acres) | Trashigang Liv. Sector |  |  | 0.08 | Direct Purchase |  | post | Plan | [11 empty] | National suplier
Actual
1.3.D.4 | Chopping machine (for dairy groups) | Purchase of Grass/Fodder Chopping Machines (40) | Trashigang Liv. Sector |  |  | 1.3 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | [5 empty] | Quatation
Actual
1.3.E.1 | Milk cans | Purchase Milk cans, Milk Buckets and sanitary items (120 Noss | Trashigang Liv. Sector |  |  | 0.6 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | [5 empty] | Quatation
Actual
1.3.E.4 | Shed construction | Purchade of CGI sheets and assoceries for 45 hygenic dairy sheds | Trashigang Liv. Sector |  |  | 0.85 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug.. 2018 | 18th Sept. 2018 | NA | [5 empty] | Quatation
Actual
|  | Purchade of cement for 45 hygenic dairy sheds | Trashigang Liv. Sector |  |  | 0.55 | Direct Purchase |  | post | Plan | [11 empty] | Dz. Agent
Actual
1.3.E.6 | Equipment dairy production groups | Purchase of 8 sets of equipments dairy production group(1 set equal to/consist of Deep freezer, Cream separator, Butter churner, 5 milk can, milking bucket, 5 cool boxes, one rim of butter/cheese packing paper, digital weighing balance, lactometer, butter/cheese moulders, aprons, hair net, face mask and cultures) | Trashigang Liv. Sector |  |  | 1.04 | NCB |  | post | Plan |  | NA | 20th July. 2018 | 2nd Aug. 2018 | 18th Sept. 2018 | [6 empty] | Quatation
Actual
1.1.A.4.a | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of Native pullets | Trashiyangtse Liv. Sector | 1 |  | 0.1 | Direct Purchase |  | post | Plan | [11 empty] | to be bought from NPPBC, Lingmethang
Actual
1.1.A.4.b | Production inputs for farm resilience and diversification (Livestock - Poultry) | Purchase of CGI sheet/Cement/wire mash | Trashiyangtse Liv. Sector | 2 |  | 0.05 | NCB |  | post | Plan | 15th Aug. 2018 |  | 20th Aug 2018 |  | 20th Sept. 2018
Actual
1.1.A.5.a | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase of Native piglets | Trashiyangtse Liv. Sector | 1 |  | 0.02 | Direct Purchase |  | post | Plan | [11 empty] | to be bought from NPPBC, Lingmethang
Actual
1.1.A.5.b | Production inputs for farm resilience and diversification (Livestock - Piggery) | Purchase shed construction materials (cement/CGI sheet) | Trashiyangtse Liv. Sector | 2 |  | 0.02 | NCB |  | Post | Plan | 15th Aug. 2018 |  | 20th Aug 2018 |  | 20th Sept. 2018
Actual
1.3.D.1.a | Perenial fodder in fallow and marginal land | Purchase of Pasture seed &seedlings | Trashiyangtse Liv. Sector | 1 |  | 0.07 | Direct Purchase |  | Post | Plan
Actual
1.3.D.1.b | Perenial fodder in fallow and marginal land | Purchase of Pasture grass-slips, cuttings | Trashiyangtse Liv. Sector | 2 |  | 0.07 | Direct Purchase |  | Post | Plan
Actual
1.3.D.2 | Winter fodder crop demonstration and seed supply | Purchase of Pasture seed &seedlings (12Acres) | Trashiyangtse Liv. Sector |  |  | 0.048 | Direct Purchase |  | post | Plan
Actual
1.3.D.4 | Chopping machine (for dairy groups) | Purchase of Grass/Fodder Chopping Machines | Trashiyangtse Liv. Sector | 1 |  | 0.132 | NCB |  | Post | Plan | 1st Aug. 2018 | NA | 15th Aug. 2018 | NA | 15th Sept. 2018 | NA
Actual
1.3.E.1 | Milk cans | Purchase Milk cans, Milk Buckets and sanitary items (120 Noss | Trashiyangtse Liv. Sector | 1 |  | 0.12 | Direct Purchase |  | post | Plan
Actual
1.3.E.4 | Shed construction | Purchade of CGI sheets and assoceries for hygenic dairy sheds | Trashiyangtse Liv. Sector | 1 |  | 0.85 | NCB |  | post | Plan | 15th Aug. 2018 |  | 20th Aug 2018 |  | 20th Sept. 2018
Actual
1.3.E.6 | Equipment dairy production groups |  | Trashiyangtse Liv. Sector | 1 |  | 0.13 | Direct Purchase |  | Post | Plan
Actual
4.1.A.4 | Scanner | 7 nos. of office snanner | OPM | 1 |  | 0.1 | NCB | post |  | Plan | [11 empty] | shall based the Annual Quatation by Ministry of Agriculture and Forests
Actual

## Services, Training &Consult
PROCUREMENT OF SERVICES, TRAINING & CONSULTANT
FOR THE PERIOD JULY 2017-JUNE 2018
| Country/Organization | : BHUTAN
| Project/Program | : Commercial Agriculture & Resilient Livelihoods Enhancement Programme
| IFAD Loan No.: 2000000627 | IFAD Grant No. : 2000000838 | ASAP Grant No. : 2000000872
[9 empty] | Request for EOI |  | Terms of reference |  | Short list |  |  | Request for proposal |  | Bid proposal |  | Bid Evaluation Technical (T) Financial (F) | [5 empty] | ContractFinalization |  |  | RGOB | Benficiary Contribution | FCBL
AWPB CODE | Component/Activity/Sub-activity | Description | Implementing Agency | Selection Method | Lumpsum or Time Based | Estimated Amount in BTN Millions | Prior or Post Review | Plan Vs Actual | Date published | Date of closing | Date proposed | Date No onjection | Date proposed | Date No objection | Plan Vs Actual | Date Proposal | Date No objection | Invitation date | submission/opening date | Submission Evaluation Report(T) | No objection Evaluation Report(T) | Opening Financial Report | Submission Eval & Financial Report (T) & (F) | No objection Evaluation Report | Plan Vs Actual | Contract Amount in US$(000) | Contract Award | Contract Signature |  |  |  | Remarks
2.3.A.1 | To conduct study on market infrastructure requirement | To hire National consultant to conduct study | RAMCO | NCB | Lumpsum | 1 | Prior | Plan | 5th August | 20th August | 15th July | 25th July | 25th August | 30th August | Plan | [11 empty] | 10th Sept | 20th Sept
2.3.A.1 | To conduct study on market infrastructure requirement | To hire National consultant to conduct study | [5 empty] | Actual